## Front Page
|  | Project and SoW description: ARGENTINA LNG Export Pipelines System |  | Company Document ID: ARLNG-019-FEL2-PBO-0000-PMG-LST-0001
Contractor Document ID: IT0061-000-ZE-00001
Vendor Document ID:
|  | Document Title: Light FEED Master Deliverables List (MDL) |  |  |  | Plant Area:
Functional Unit:
Issue Date: 16/10/25
|  | Facility & Sub Facility Description: |  |  |  | Sheet 1 |  | of 2
Rev.: A
ARGENTINA LNG – Export Pipelines System
Light FEED Master Deliverables List (MDL)
A | 2025-10-16 |  | ISSUED FOR INFORMATION |  | CB |  | MR | GR
Rev | Date |  | Description |  | Prepared by |  | Revised by | Approved by

## BNT DOCUMENT LIST
ARGENTINA LNG – Export Pipelines System
MASTER DOCUMENT REGISTER (MDR)
[5 empty] | WBS |  |  | Entities |  |  |  |  | BONATTI | [13 empty] | TRANSMITTAL OUT to CLIENT |  |  | TRANSMITTAL IN from CLIENT |  |  | TRANSMITTAL OUT to 3rd Parties |  |  | TRANSMITTAL IN from 3rd Parties |  |  | TRANSMITTAL OUT to SITE |  |  | TRANSMITTAL IN from SITE |  |  |  | IFA/IFI |  |  | FINAL APPROVAL by CLIENT |  |  | FIN |  |  | FINAL APPROVAL |  |  | PROGRESS |  |  |  | Progress Percentage
ID Counter | Project Code | Main Area | Discipline | Work Category | Activity Id | Activity Description | ORIGINAL ID | Owner | PO reference | Subject Code | Document Type | Numeric Code | BONATTI's DOCUMENT NUMBER | Plant/Project | Package Number | Project Phase | Organisation Code | Unit/Facility Code | Discipline Code | Document Type | CLIENT's DOCUMENT ID | Document Title | Latest Rev. | Int. Rev. | Latest STEP | Document Class | Transmittal Code Id | Date | Issuing Reason | Transmittal Code Id | Date | Review Code | Transmittal Code Id | Date | Issuing Reason | Transmittal Code Id | Date | Review Code | Transmittal Code Id | Date | Issuing Reason | Transmittal Code Id | Date | Review Code | Planned | Forecast | Actual | Planned | Forecast | Actual | Planned | Forecast | Actual | Planned | Forecast | Actual | Engineering Progress | Mhs | Supplier Progress | Mhs | Cumulative Planned % | Cumulative Forecast % | Cumulative Actual %
<N> | .idcommessa2 | .ImpiantoGuid | .codeDisciplina | .Text10 | .WBSGuid | .Desc_Wbs | .Text1 | .OrigineDocumento | .NumeroOrdine | .argomentoguid | .tipodocguid | .progressivo | .CodDocInterno | .Text2 | .Text3 | .Text4 | .Text5 | .Text6 | .Text7 | .Text8 | .CodDocCliente | .Titolo | .Rev | .RevInterna | .stepGuid | .Categoria | .fnd_TrasmittalOut | .fnd_TrasmDataInvio | .fnd_RispostaOut | .fnd_TrasmittalIn | .fnd_TrasmDataRicez | .fnd_TrasmittalInReturnCode | .fnd_TrasmittalInSupplier | .fnd_TrasmittalInSupplierData | .fnd_TrasmittalInSupplierReturnCode | .fnd_TrasmittalOutSupplier | .fnd_TrasmittalOutSupplierDate | .fnd_TrasmittalOutSupplierCode | .fnd_TrasmittalInSite | .fnd_TrasmittalInSiteData | .fnd_TrasmittalInSiteReturnCode | .fnd_TrasmittalOutSite | .fnd_TrasmittalOutSiteDate | .fnd_TrasmittalOutSiteCode | .Data_planned1 | .data_forecast1 | .Data_Actual1 | .Data_planned2 | .Data_Forecast2 | .Data_Actual2 | .Data_planned3 | .Data_Forecast3 | .Data_Actual3 | .Data_planned4 | .Data_Forecast4 | .Data_Actual4 | .progress | .BudgetOre | .ProgressFornitore | .BudgetOreFornitore | .PercPlanned | .PercForecast | .PercActual
1 | IT0061 | 000 | PM |  |  |  | 116 | PLA |  | Z | E | 00001 | IT0061-000-ZE-00001 | ARLNG | 019 | FEL2 | PBO | 0000 | PMG | LST | ARLNG-019-FEL2-PBO-0000-PMG-LST-0001 | Light FEED Master Deliverables List (MDL) | A | 0 | INF | O | [18 empty] | 2025-10-17 |  |  | 2025-10-24 | [8 empty] | YES | 100 | NO
2 | IT0061 | 000 | PM |  |  |  | 117 | PLA |  | Z | G | 00002 | IT0061-000-ZG-00002 | ARLNG | 019 | FEL2 | PBO | 0000 | PMG | PLN | ARLNG-019-FEL2-PBO-0000-PMG-PLN-0001 | Light FEED PEP | A | 0 | INF | O | [18 empty] | 2025-12-19 |  |  | 2025-12-26 | [8 empty] | YES | 75 | NO
3 | IT0061 | 000 | PM |  |  |  | 119 | PLA |  | Z | G | 00003 | IT0061-000-ZG-00003 | ARLNG | 019 | FEL2 | PBO | 0000 | HSE | LYT | ARLNG-019-FEL2-PBO-0000-HSE-LYT-0001 | Light FEED HSSE Management Plan | A | 0 | INF | O | [18 empty] | 2025-12-19 |  |  | 2025-12-26 | [8 empty] | YES | 75 | NO
4 | IT0061 | 000 | PM |  |  |  | 120 | PLA |  | Z | G | 00004 | IT0061-000-ZG-00004 | ARLNG | 019 | FEL2 | PBO | 0000 | QAC | PLN | ARLNG-019-FEL2-PBO-0000-QAC-PLN-0001 | Light FEED Quality Management Plan | A | 0 | INF | O | [18 empty] | 2025-12-19 |  |  | 2025-12-26 | [8 empty] | YES | 75 | NO
5 | IT0061 | 000 | PM |  |  |  | 115 | PLA |  | Z | G | 00005 | IT0061-000-ZG-00005 | ARLNG | 019 | FEL2 | PBO | 0000 | PLG | SCH | ARLNG-019-FEL2-PBO-0000-PLG-SCH-0002 | Light FEED Detail Schedule | A | 0 | INF | O | [18 empty] | 2025-12-19 |  |  | 2025-12-26 | [8 empty] | YES | 75 | NO
6 | IT0061 | 000 | PM |  |  |  | 111 | PLA |  | Z | B | 00006 | IT0061-000-ZB-00006 | ARLNG | 019 | FEL2 | PBO | 0000 | PMG | RPT | ARLNG-019-FEL2-PBO-0000-PMG-RPT-0001 | Light FEED Close-out Report | A | 0 | INF | O | [18 empty] | 2025-12-19 |  |  | 2025-12-26 | [8 empty] | YES | 75 | NO
7 | IT0061 | 000 | PM |  |  |  | 121 | PLA |  | Z | G | 00007 | IT0061-000-ZG-00007 | ARLNG | 019 | FEL2 | PBO | 0000 | PLG | CBE | ARLNG-019-FEL2-PBO-0000-PLG-CBE-0001 | EPC Progressive Lump Sum Technical and Commercial Offer with a binding price with a maximum deviation | A | 0 | INF | O | [18 empty] | 2025-12-19 |  |  | 2025-12-26 | [8 empty] | YES | 75 | NO
8 | IT0061 | 000 | PM |  |  |  | 113 | PLA |  | Z | B | 00008 | IT0061-000-ZB-00008 | ARLNG | 019 | FEL2 | PBO | 0000 | PMG | SOW | ARLNG-019-FEL2-PBO-0000-PMG-SOW-0001 | EPC Scope of Works | A | 0 | INF | O | [18 empty] | 2025-12-19 |  |  | 2025-12-26 | [8 empty] | YES | 75 | NO
9 | IT0061 | 000 | PM |  |  |  | 118 | PLA |  | Z | G | 00009 | IT0061-000-ZG-00009 | ARLNG | 019 | FEL2 | PBO | 0000 | PMG | PLN | ARLNG-019-FEL2-PBO-0000-PMG-PLN-0002 | PEP EPC Phase | A | 0 | INF | O | [18 empty] | 2025-12-19 |  |  | 2025-12-26 | [8 empty] | YES | 75 | NO
10 | IT0061 | 000 | PM |  |  |  | 123 | PLA |  | Z | G | 00010 | IT0061-000-ZG-00010 | ARLNG | 019 | FEL2 | PBO | 0000 | PRO | PLN | ARLNG-019-FEL2-PBO-0000-PRO-PLN-0001 | Procurement Plan for EPC phase | A | 0 | INF | O | [18 empty] | 2025-12-19 |  |  | 2025-12-26 | [8 empty] | YES | 75 | NO
11 | IT0061 | 000 | PM |  |  |  | 112 | PLA |  | Z | G | 00011 | IT0061-000-ZG-00011 | ARLNG | 019 | FEL2 | PBO | 0000 | PLG | SCH | ARLNG-019-FEL2-PBO-0000-PLG-SCH-0001 | EPC Detail Schedule | A | 0 | INF | O | [18 empty] | 2025-12-19 |  |  | 2025-12-26 | [8 empty] | YES | 75 | NO
12 | IT0061 | 000 | PM |  |  |  | 114 | PLA |  | Z | B | 00012 | IT0061-000-ZB-00012 | ARLNG | 019 | FEL2 | PBO | 0000 | PRO | DES | ARLNG-019-FEL2-PBO-0000-PRO-DES-0001 | EPC Basis of Design | A | 0 | INF | O | [18 empty] | 2025-12-19 |  |  | 2025-12-26 | [8 empty] | YES | 75 | NO
13 | IT0061 | 000 | PM |  |  |  | 128 | PLA |  | Z | G | 00013 | IT0061-000-ZG-00013 | ARLNG | 019 | FEL2 | PBO | 0000 | HSE | RPT | ARLNG-019-FEL2-PBO-0000-HSE-RPT-0001 | Environmental Data Book | A | 0 | INF | O | [18 empty] | 2025-12-19 |  |  | 2025-12-26 | [8 empty] | YES | 94 | NO
14 | IT0061 | 000 | PM |  |  |  | 91 | PLA |  | Z | B | 00014 | IT0061-000-ZB-00014 | ARLNG | 019 | FEL2 | PBO | 0000 | PRO | DES | ARLNG-019-FEL2-PBO-0000-PRO-DES-0002 | LIGHT FEED Basis of Design for all disciplines | A | 0 | IFA | X | [18 empty] | 2025-11-14 |  |  | 2025-11-21 |  |  | 2025-11-28 |  |  | 2025-12-05 |  |  | YES | 125 | NO
15 | IT0061 | 000 | PR |  |  |  | 90 | PLA |  | A | B | 00015 | IT0061-000-AB-00015 | ARLNG | 019 | FEL2 | PBO | 0000 | PRO | RPT | ARLNG-019-FEL2-PBO-0000-PRO-RPT-0001 | Hydraulic Calculation Report (pressure profile definition, Compressor Stations number and location definition) | A | 0 | INF | O | [18 empty] | 2025-11-14 |  |  | 2025-11-21 | [8 empty] | YES | 125 | NO
16 | IT0061 | 005 | PR |  |  |  | 104 | PLA |  | A | C | 00016 | IT0061-005-AC-00016 | ARLNG | 019 | FEL2 | PBO | 0000 | PRO | PFD | ARLNG-019-FEL2-PBO-0000-PRO-PFD-0002 | Process Flow Diagrams and H&MB (Compresor Station) | A | 0 | IFA | X | [18 empty] | 2025-11-14 |  |  | 2025-11-21 |  |  | 2025-11-28 |  |  | 2025-12-05 |  |  | YES | 125 | NO
17 | IT0061 | 006 | PR |  |  |  | 104 | PLA |  | A | C | 00017 | IT0061-006-AC-00017 | ARLNG | 019 | FEL2 | PBO | 0000 | PRO | PFD | ARLNG-019-FEL2-PBO-0000-PRO-PFD-0001 | Process Flow Diagrams and H&MB (Central Hub) | A | 0 | IFA | X | [18 empty] | 2025-11-14 |  |  | 2025-11-21 |  |  | 2025-11-28 |  |  | 2025-12-05 |  |  | YES | 125 | NO
18 | IT0061 | 005 | PR |  |  |  | 106 | PLA |  | A | C | 00018 | IT0061-005-AC-00018 | ARLNG | 019 | FEL2 | PBO | 0000 | PRO | UFD | ARLNG-019-FEL2-PBO-0000-PRO-UFD-0002 | Utilities Flow Diagrams (Compressor Station) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 75 | NO
19 | IT0061 | 006 | PR |  |  |  | 106 | PLA |  | A | C | 00019 | IT0061-006-AC-00019 | ARLNG | 019 | FEL2 | PBO | 0000 | PRO | UFD | ARLNG-019-FEL2-PBO-0000-PRO-UFD-0001 | Utilities Flow Diagrams (Central Hub) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 75 | NO
20 | IT0061 | 005 | PR |  |  |  | 107 | PLA |  | A | C | 00020 | IT0061-005-AC-00020 | ARLNG | 019 | FEL2 | PBO | 0000 | PRO | PID | ARLNG-019-FEL2-PBO-0000-PRO-PID-0003 | Piping & Instrument Diagrams (Compressor Station) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
21 | IT0061 | 006 | PR |  |  |  | 107 | PLA |  | A | C | 00021 | IT0061-006-AC-00021 | ARLNG | 019 | FEL2 | PBO | 0000 | PRO | PID | ARLNG-019-FEL2-PBO-0000-PRO-PID-0002 | Piping & Instrument Diagrams (Central Hub) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
22 | IT0061 | 007 | PR |  |  |  | 107 | PLA |  | A | C | 00022 | IT0061-007-AC-00022 | ARLNG | 019 | FEL2 | PBO | 0000 | PRO | PID | ARLNG-019-FEL2-PBO-0000-PRO-PID-0001 | Piping & Instrument Diagrams (BVS, Scraper trap) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
23 | IT0061 | 005 | PR |  |  |  | 93 | PLA |  | A | E | 00023 | IT0061-005-AE-00023 | ARLNG | 019 | FEL2 | PBO | 0000 | PRO | RPT | ARLNG-019-FEL2-PBO-0000-PRO-RPT-0005 | Process Equipment Summary (Compressor Station) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
24 | IT0061 | 006 | PR |  |  |  | 93 | PLA |  | A | E | 00024 | IT0061-006-AE-00024 | ARLNG | 019 | FEL2 | PBO | 0000 | PRO | RPT | ARLNG-019-FEL2-PBO-0000-PRO-RPT-0004 | Process Equipment Summary (Central Hub) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
25 | IT0061 | 005 | PR |  |  |  | 50 | PLA |  | A | B | 00025 | IT0061-005-AB-00025 | ARLNG | 019 | FEL2 | PBO | 0000 | PRO | TDS | ARLNG-019-FEL2-PBO-0000-PRO-TDS-0002 | Datasheet for GAS SRUBBERS (Compressor Station) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
26 | IT0061 | 005 | PR |  |  |  | 50 | PLA |  | A | B | 00026 | IT0061-005-AB-00026 | ARLNG | 019 | FEL2 | PBO | 0000 | PRO | TDS | ARLNG-019-FEL2-PBO-0000-PRO-TDS-0001 | Datasheet for AIRCOOLERS (Compressor Station) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
27 | IT0061 | 006 | PR |  |  |  | 50 | PLA |  | A | B | 00027 | IT0061-006-AB-00027 | ARLNG | 019 | FEL2 | PBO | 0000 | PRO | TDS | ARLNG-019-FEL2-PBO-0000-PRO-TDS-0003 | Datasheet for STOREGE TANKS (Central Hub) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
28 | IT0061 | 005 | PR |  |  |  | 59 | PLA |  | A | B | 00028 | IT0061-005-AB-00028 | ARLNG | 019 | FEL2 | PBO | 0000 | PRO | TDS | ARLNG-019-FEL2-PBO-0000-PRO-TDS-0004 | Datasheet for TURBOCOMPRESSORS (Compressor Station) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
29 | IT0061 | 005 | PR |  |  |  | 103 | PLA |  | A | B | 00029 | IT0061-005-AB-00029 | ARLNG | 019 | FEL2 | PBO | 0000 | PRO | CAL | ARLNG-019-FEL2-PBO-0000-PRO-CAL-0002 | Process Equipment Calculation Note (Compressor Station) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 75 | NO
30 | IT0061 | 006 | PR |  |  |  | 103 | PLA |  | A | B | 00030 | IT0061-006-AB-00030 | ARLNG | 019 | FEL2 | PBO | 0000 | PRO | CAL | ARLNG-019-FEL2-PBO-0000-PRO-CAL-0001 | Process Equipment Calculation Note (Central Hub) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 75 | NO
31 | IT0061 | 005 | PR |  |  |  | 108 | PLA |  | A | B | 00031 | IT0061-005-AB-00031 | ARLNG | 019 | FEL2 | PBO | 0000 | PRO | RPT | ARLNG-019-FEL2-PBO-0000-PRO-RPT-0003 | Pressure relieving system calculation report (Compressor Station) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 75 | NO
32 | IT0061 | 006 | PR |  |  |  | 108 | PLA |  | A | B | 00032 | IT0061-006-AB-00032 | ARLNG | 019 | FEL2 | PBO | 0000 | PRO | RPT | ARLNG-019-FEL2-PBO-0000-PRO-RPT-0002 | Pressure relieving system calculation report (Central Hub) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 75 | NO
33 | IT0061 | 005 | PR |  |  |  | 101 | PLA |  | A | B | 00033 | IT0061-005-AB-00033 | ARLNG | 019 | FEL2 | PBO | 0000 | PRO | STR | ARLNG-019-FEL2-PBO-0000-PRO-STR-0002 | Operation and Control Philosophy (Compressor Station) | A | 0 | INF | O | [18 empty] | 2025-12-19 |  |  | 2025-12-26 | [8 empty] | YES | 75 | NO
34 | IT0061 | 006 | PR |  |  |  | 101 | PLA |  | A | B | 00034 | IT0061-006-AB-00034 | ARLNG | 019 | FEL2 | PBO | 0000 | PRO | STR | ARLNG-019-FEL2-PBO-0000-PRO-STR-0001 | Operation and Control Philosophy (Central Hub) | A | 0 | INF | O | [18 empty] | 2025-12-19 |  |  | 2025-12-26 | [8 empty] | YES | 75 | NO
35 | IT0061 | 005 | SE |  |  |  | 24 | PLA |  | F | C | 00035 | IT0061-005-FC-00035 | ARLNG | 019 | FEL2 | PBO | 0000 | PSM | LYT | ARLNG-019-FEL2-PBO-0000-PSM-LYT-0005 | Hazardous area classification layout (Compressor Station) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
36 | IT0061 | 006 | SE |  |  |  | 24 | PLA |  | F | C | 00036 | IT0061-006-FC-00036 | ARLNG | 019 | FEL2 | PBO | 0000 | PSM | LYT | ARLNG-019-FEL2-PBO-0000-PSM-LYT-0004 | Hazardous area classification layout (Central Hub) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
37 | IT0061 | 007 | SE |  |  |  | 24 | PLA |  | F | C | 00037 | IT0061-007-FC-00037 | ARLNG | 019 | FEL2 | PBO | 0000 | PSM | LYT | ARLNG-019-FEL2-PBO-0000-PSM-LYT-0003 | Hazardous area classification layout (BVS, scraper trap) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
38 | IT0061 | 005 | SE |  |  |  | 96 | PLA |  | F | C | 00038 | IT0061-005-FC-00038 | ARLNG | 019 | FEL2 | PBO | 0000 | PSM | LYT | ARLNG-019-FEL2-PBO-0000-PSM-LYT-0002 | Firefighting Layout - network and equipment (Compressor Station) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
39 | IT0061 | 006 | SE |  |  |  | 96 | PLA |  | F | C | 00039 | IT0061-006-FC-00039 | ARLNG | 019 | FEL2 | PBO | 0000 | PSM | LYT | ARLNG-019-FEL2-PBO-0000-PSM-LYT-0001 | Firefighting Layout - network and equipment (Central Hub) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
40 | IT0061 | 000 | SE |  |  |  | 33 | PLA |  | F | B | 00040 | IT0061-000-FB-00040 | ARLNG | 019 | FEL2 | PBO | 0000 | PSM | HAZ | ARLNG-019-FEL2-PBO-0000-PSM-HAZ-0001 | HAZID | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
41 | IT0061 | 000 | SE |  |  |  | 127 | PLA |  | F | B | 00041 | IT0061-000-FB-00041 | ARLNG | 019 | FEL2 | PBO | 0000 | PSM | RPT | ARLNG-019-FEL2-PBO-0000-PSM-RPT-0001 | EAC + ACR | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
42 | IT0061 | 005 | TB |  |  |  | 62 | PLA |  | P | C | 00042 | IT0061-005-PC-00042 | ARLNG | 019 | FEL2 | PBO | 0000 | PIP | LYT | ARLNG-019-FEL2-PBO-0000-PIP-LYT-0003 | Overall Plot Plan (Compressor Stations) | A | 0 | IFA | X | [18 empty] | 2025-11-14 |  |  | 2025-11-21 |  |  | 2025-11-28 |  |  | 2025-12-05 |  |  | YES | 125 | NO
43 | IT0061 | 006 | TB |  |  |  | 63 | PLA |  | P | C | 00043 | IT0061-006-PC-00043 | ARLNG | 019 | FEL2 | PBO | 0000 | PIP | LYT | ARLNG-019-FEL2-PBO-0000-PIP-LYT-0002 | Overall Plot Plan (Central Hub) | A | 0 | IFA | X | [18 empty] | 2025-11-14 |  |  | 2025-11-21 |  |  | 2025-11-28 |  |  | 2025-12-05 |  |  | YES | 125 | NO
44 | IT0061 | 007 | TB |  |  |  | 64 | PLA |  | P | C | 00044 | IT0061-007-PC-00044 | ARLNG | 019 | FEL2 | PBO | 0000 | PIP | LYT | ARLNG-019-FEL2-PBO-0000-PIP-LYT-0001 | Overall Plot Plan (BVS, scraper traps) | A | 0 | IFA | X | [18 empty] | 2025-11-14 |  |  | 2025-11-21 |  |  | 2025-11-28 |  |  | 2025-12-05 |  |  | YES | 125 | NO
45 | IT0061 | 000 | TB |  |  |  | 56 | PLA |  | P | B | 00045 | IT0061-000-PB-00045 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | STR | ARLNG-019-FEL2-PBO-0000-PLF-STR-0001 | Material selection philosophy | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
46 | IT0061 | 000 | TB |  |  |  | 67 | PLA |  | P | B | 00046 | IT0061-000-PB-00046 | ARLNG | 019 | FEL2 | PBO | 0000 | PIP | RPT | ARLNG-019-FEL2-PBO-0000-PIP-RPT-0001 | Summary of the pipe classes of the project. | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
47 | IT0061 | 000 | TB |  |  |  | 69 | PLA |  | P | B | 00047 | IT0061-000-PB-00047 | ARLNG | 019 | FEL2 | PBO | 0000 | PIP | TDS | ARLNG-019-FEL2-PBO-0000-PIP-TDS-0001 | Simplified Data Sheet for Manual Valves | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
48 | IT0061 | 005 | CV |  |  |  | 6 | PLA |  | C | E | 00048 | IT0061-005-CE-00048 | ARLNG | 019 | FEL2 | PBO | 0000 | ARC | LST | ARLNG-019-FEL2-PBO-0000-ARC-LST-0002 | Buildings - Summary List (Compressor Station) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
49 | IT0061 | 006 | CV |  |  |  | 6 | PLA |  | C | E | 00049 | IT0061-006-CE-00049 | ARLNG | 019 | FEL2 | PBO | 0000 | ARC | LST | ARLNG-019-FEL2-PBO-0000-ARC-LST-0001 | Buildings - Summary List (Central Hub) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
50 | IT0061 | 005 | CV |  |  |  | 5 | PLA |  | C | C | 00050 | IT0061-005-CC-00050 | ARLNG | 019 | FEL2 | PBO | 0000 | ARC | LYT | ARLNG-019-FEL2-PBO-0000-ARC-LYT-0002 | Buildings - General Layout -preliminary footprint and orientation (Compressor Station) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 75 | NO
51 | IT0061 | 006 | CV |  |  |  | 5 | PLA |  | C | C | 00051 | IT0061-006-CC-00051 | ARLNG | 019 | FEL2 | PBO | 0000 | ARC | LYT | ARLNG-019-FEL2-PBO-0000-ARC-LYT-0001 | Buildings - General Layout -preliminary footprint and orientation (Central Hub) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 75 | NO
52 | IT0061 | 005 | CV |  |  |  | 7 | PLA |  | C | C | 00052 | IT0061-005-CC-00052 | ARLNG | 019 | FEL2 | PBO | 0000 | ARC | DWG | ARLNG-019-FEL2-PBO-0000-ARC-DWG-0002 | Buildings - Architectural typical drawings (Compressor Station) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 75 | NO
53 | IT0061 | 006 | CV |  |  |  | 7 | PLA |  | C | C | 00053 | IT0061-006-CC-00053 | ARLNG | 019 | FEL2 | PBO | 0000 | ARC | DWG | ARLNG-019-FEL2-PBO-0000-ARC-DWG-0001 | Buildings - Architectural typical drawings (Central Hub) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 75 | NO
54 | IT0061 | 005 | CV |  |  |  | 8 | PLA |  | C | B | 00054 | IT0061-005-CB-00054 | ARLNG | 019 | FEL2 | PBO | 0000 | STC | CAL | ARLNG-019-FEL2-PBO-0000-STC-CAL-0002 | Steel Structures - Preliminary sizing (Compressor Station) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 75 | NO
55 | IT0061 | 006 | CV |  |  |  | 8 | PLA |  | C | B | 00055 | IT0061-006-CB-00055 | ARLNG | 019 | FEL2 | PBO | 0000 | STC | CAL | ARLNG-019-FEL2-PBO-0000-STC-CAL-0001 | Steel Structures - Preliminary sizing (Central Hub) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 75 | NO
56 | IT0061 | 005 | CV |  |  |  | 9 | PLA |  | C | B | 00056 | IT0061-005-CB-00056 | ARLNG | 019 | FEL2 | PBO | 0000 | CVS | CAL | ARLNG-019-FEL2-PBO-0000-CVS-CAL-0002 | Foundations - Preliminary sizing (Compressor Station) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 75 | NO
57 | IT0061 | 006 | CV |  |  |  | 9 | PLA |  | C | B | 00057 | IT0061-006-CB-00057 | ARLNG | 019 | FEL2 | PBO | 0000 | CVS | CAL | ARLNG-019-FEL2-PBO-0000-CVS-CAL-0001 | Foundations - Preliminary sizing (Central Hub) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 75 | NO
58 | IT0061 | 005 | CV |  |  |  | 10 | PLA |  | C | C | 00058 | IT0061-005-CC-00058 | ARLNG | 019 | FEL2 | PBO | 0000 | CVS | LYT | ARLNG-019-FEL2-PBO-0000-CVS-LYT-0002 | Foundations - Preliminary General Layout (Compressor Station) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 75 | NO
59 | IT0061 | 006 | CV |  |  |  | 10 | PLA |  | C | C | 00059 | IT0061-006-CC-00059 | ARLNG | 019 | FEL2 | PBO | 0000 | CVS | LYT | ARLNG-019-FEL2-PBO-0000-CVS-LYT-0001 | Foundations - Preliminary General Layout (Central Hub) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 75 | NO
60 | IT0061 | 000 | EL |  |  |  | 20 | PLA |  | E | B | 00060 | IT0061-000-EB-00060 | ARLNG | 019 | FEL2 | PBO | 0000 | ELE | RPT | ARLNG-019-FEL2-PBO-0000-ELE-RPT-0001 | Electrical studies (power source and availability) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 75 | NO
61 | IT0061 | 005 | EL |  |  |  | 25 | PLA |  | E | B | 00061 | IT0061-005-EB-00061 | ARLNG | 019 | FEL2 | PBO | 0000 | ELE | LST | ARLNG-019-FEL2-PBO-0000-ELE-LST-0003 | Electrical load list and load balance (Compressor Station) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
62 | IT0061 | 006 | EL |  |  |  | 25 | PLA |  | E | B | 00062 | IT0061-006-EB-00062 | ARLNG | 019 | FEL2 | PBO | 0000 | ELE | LST | ARLNG-019-FEL2-PBO-0000-ELE-LST-0002 | Electrical load list and load balance (Central Hub) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
63 | IT0061 | 007 | EL |  |  |  | 25 | PLA |  | E | B | 00063 | IT0061-007-EB-00063 | ARLNG | 019 | FEL2 | PBO | 0000 | ELE | LST | ARLNG-019-FEL2-PBO-0000-ELE-LST-0001 | Electrical load list and load balance (BVS, scraper trap) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
64 | IT0061 | 005 | EL |  |  |  | 23 | PLA |  | E | C | 00064 | IT0061-005-EC-00064 | ARLNG | 019 | FEL2 | PBO | 0000 | ELE | SLD | ARLNG-019-FEL2-PBO-0000-ELE-SLD-0003 | Single-line diagrams (Compresso Station) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
65 | IT0061 | 006 | EL |  |  |  | 23 | PLA |  | E | C | 00065 | IT0061-006-EC-00065 | ARLNG | 019 | FEL2 | PBO | 0000 | ELE | SLD | ARLNG-019-FEL2-PBO-0000-ELE-SLD-0002 | Single-line diagrams (Cental Hub) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
66 | IT0061 | 007 | EL |  |  |  | 23 | PLA |  | E | C | 00066 | IT0061-007-EC-00066 | ARLNG | 019 | FEL2 | PBO | 0000 | ELE | SLD | ARLNG-019-FEL2-PBO-0000-ELE-SLD-0001 | Single-line diagrams (BVS, scraper trap) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
67 | IT0061 | 000 | SA |  |  |  | 37 | PLA |  | S | C | 00067 | IT0061-000-SC-00067 | ARLNG | 019 | FEL2 | PBO | 0000 | INS | DWG | ARLNG-019-FEL2-PBO-0000-INS-DWG-0003 | Control system architecture, safety, F&G and other systems (Overall) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
68 | IT0061 | 005 | SA |  |  |  | 37 | PLA |  | S | C | 00068 | IT0061-005-SC-00068 | ARLNG | 019 | FEL2 | PBO | 0000 | INS | DWG | ARLNG-019-FEL2-PBO-0000-INS-DWG-0002 | Control system architecture, safety, F&G and other systems (Compressor Station) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
69 | IT0061 | 006 | SA |  |  |  | 37 | PLA |  | S | C | 00069 | IT0061-006-SC-00069 | ARLNG | 019 | FEL2 | PBO | 0000 | INS | DWG | ARLNG-019-FEL2-PBO-0000-INS-DWG-0001 | Control system architecture, safety, F&G and other systems (Central Hub) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
70 | IT0061 | 000 | SA |  |  |  | 44 | PLA |  | S | B | 00070 | IT0061-000-SB-00070 | ARLNG | 019 | FEL2 | PBO | 0000 | INS | SPC | ARLNG-019-FEL2-PBO-0000-INS-SPC-0002 | Technical Specification of Integrated Control and Safety System (ICSS) Design (Including DCS, SIS and FGS) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
71 | IT0061 | 000 | SA |  |  |  | 41 | PLA |  | S | B | 00071 | IT0061-000-SB-00071 | ARLNG | 019 | FEL2 | PBO | 0000 | INS | SPC | ARLNG-019-FEL2-PBO-0000-INS-SPC-0001 | Technical Specification of Custody Metering | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
72 | IT0061 | 000 | SA |  |  |  | 76 | PLA |  | S | B | 00072 | IT0061-000-SB-00072 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | SPC | ARLNG-019-FEL2-PBO-0000-PLF-SPC-0007 | Specification for pipeline valves | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 100 | NO
73 | IT0061 | 000 | SM |  |  |  | 17 | PLA |  | X | X | 00073 | IT0061-000-XX-00073 | ARLNG | 019 | FEL2 | PBO | 0000 | CON | RPT | ARLNG-019-FEL2-PBO-0000-CON-RPT-0001 | Constructability & Logistics Preliminary Study | A | 0 | INF | O | [18 empty] | 2025-12-19 |  |  | 2025-12-26 | [8 empty] | YES | 75 | NO
74 | IT0061 | 000 | SM |  |  |  | 18 | PLA |  | X | X | 00074 | IT0061-000-XX-00074 | ARLNG | 019 | FEL2 | PBO | 0000 | CON | STR | ARLNG-019-FEL2-PBO-0000-CON-STR-0001 | EPC execution strategy (nbr. of spreads, main equipment) | A | 0 | INF | O | [18 empty] | 2025-12-19 |  |  | 2025-12-26 | [8 empty] | YES | 75 | NO
75 | IT0061 | 000 | SM |  |  |  | 122 | PIP |  | X | X | 00075 | IT0061-000-XX-00075 | ARLNG | 019 | FEL2 | PBO | 0000 | CON | STR | ARLNG-019-FEL2-PBO-0000-CON-STR-0002 | Strategy for hydraulic test, dimensional control and drying | A | 0 | INF | O | [18 empty] | 2025-12-19 |  |  | 2025-12-26 | [8 empty] | YES | 60 | NO
76 | IT0061 | 000 | PL |  |  |  | 104 | PIP |  | L | C | 00076 | IT0061-000-LC-00076 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DGM | ARLNG-019-FEL2-PBO-0000-PLF-DGM-0001 | Overall Pipeline schematic diagram | A | 0 | IFA | X | [18 empty] | 2025-11-14 |  |  | 2025-11-21 |  |  | 2025-11-28 |  |  | 2025-12-05 |  |  | YES | 48 | NO
77 | IT0061 | 000 | PL |  |  |  | 71 | PIP |  | L | B | 00077 | IT0061-000-LB-00077 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DES | ARLNG-019-FEL2-PBO-0000-PLF-DES-0001 | Design Criteria for pipelines | A | 0 | IFA | X | [18 empty] | 2025-11-14 |  |  | 2025-11-21 |  |  | 2025-11-28 |  |  | 2025-12-05 |  |  | YES | 80 | NO
78 | IT0061 | 000 | EL |  |  |  | 32 | PIP |  | E | B | 00078 | IT0061-000-EB-00078 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DES | ARLNG-019-FEL2-PBO-0000-PLF-DES-0002 | Pipeline Cathodic Protection Basis of Design | A | 0 | IFA | X | [18 empty] | 2025-11-14 |  |  | 2025-11-21 |  |  | 2025-11-28 |  |  | 2025-12-05 |  |  | YES | 80 | NO
79 | IT0061 | 000 | PL |  |  |  | 109 | PIP |  | L | B | 00079 | IT0061-000-LB-00079 | ARLNG | 019 | FEL2 | PBO | 0000 | CMM | STR | ARLNG-019-FEL2-PBO-0000-CMM-STR-0001 | Pipeline pre-Commissioning and Commissioning Philosophy | A | 0 | INF | O | [18 empty] | 2025-12-19 |  |  | 2025-12-26 | [8 empty] | YES | 60 | NO
80 | IT0061 | 000 | CV |  |  |  | 3 | PIP |  | C | B | 00080 | IT0061-000-CB-00080 | ARLNG | 019 | FEL2 | PBO | 0000 | CVS | RPT | ARLNG-019-FEL2-PBO-0000-CVS-RPT-0002 | Geotechnical Investigation - Scope of Work for LIGHT FEED soil investigation analysis | A | 0 | INF | O | [18 empty] | 2025-12-19 |  |  | 2025-12-26 | [8 empty] | YES | 40 | NO
81 | IT0061 | 000 | CV |  |  |  | 4 | PIP |  | C | B | 00081 | IT0061-000-CB-00081 | ARLNG | 019 | FEL2 | PBO | 0000 | CVS | RPT | ARLNG-019-FEL2-PBO-0000-CVS-RPT-0001 | Geotechnical Investigation - Data interpretation Report (desktop study) | A | 0 | INF | O | [18 empty] | 2025-11-14 |  |  | 2025-11-21 | [8 empty] | YES | 80 | NO
82 | IT0061 | 000 | CV |  |  |  | 12 | PIP |  | C | B | 00082 | IT0061-000-CB-00082 | ARLNG | 019 | FEL2 | PBO | 0000 | CVS | RPT | ARLNG-019-FEL2-PBO-0000-CVS-RPT-0003 | Topographic Survey - Scope of Work and Technical Requirements for LIGHT FEED | A | 0 | INF | O | [18 empty] | 2025-11-14 |  |  | 2025-11-21 | [8 empty] | YES | 40 | NO
83 | IT0061 | 000 | PL |  |  |  | 80 | PIP |  | L | B | 00083 | IT0061-000-LB-00083 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | RPT | ARLNG-019-FEL2-PBO-0000-PLF-RPT-0003 | Pipelines Thickness Calculation and Selection Report | A | 0 | INF | O | [18 empty] | 2025-11-14 |  |  | 2025-11-21 | [8 empty] | YES | 60 | NO
84 | IT0061 | 000 | PL |  |  |  | 82 | PIP |  | L | B | 00084 | IT0061-000-LB-00084 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | RPT | ARLNG-019-FEL2-PBO-0000-PLF-RPT-0001 | Buoyancy Calculation Report | A | 0 | INF | O | [18 empty] | 2025-11-14 |  |  | 2025-11-21 | [8 empty] | YES | 60 | NO
85 | IT0061 | 000 | PL |  |  |  | 87 | PIP |  | L | C | 00085 | IT0061-000-LC-00085 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | PLN | ARLNG-019-FEL2-PBO-0000-PLF-PLN-0001 | Overall Pipelines Route Plan | A | 0 | IFA | X | [18 empty] | 2025-11-14 |  |  | 2025-11-21 |  |  | 2025-11-28 |  |  | 2025-12-05 |  |  | YES | 60 | NO
86 | IT0061 | 000 | CV |  |  |  | 13 | PIP |  | C | C | 00086 | IT0061-000-CC-00086 | ARLNG | 019 | FEL2 | PBO | 0000 | CVS | DWG | ARLNG-019-FEL2-PBO-0000-CVS-DWG-0001 | Access roads and circulation plan (based on .kmz) | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 60 | NO
87 | IT0061 | 000 | CV |  |  |  | 14 | PIP |  | C | C | 00087 | IT0061-000-CC-00087 | ARLNG | 019 | FEL2 | PBO | 0000 | CVS | PLN | ARLNG-019-FEL2-PBO-0000-CVS-PLN-0001 | Earthworks - Preliminary Soil Movement Plan | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 60 | NO
88 | IT0061 | 000 | PL |  |  |  | 81 | PIP |  | L | B | 00088 | IT0061-000-LB-00088 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | RPT | ARLNG-019-FEL2-PBO-0000-PLF-RPT-0002 | Special Crossings Design report | A | 0 | INF | O | [18 empty] | 2025-12-19 |  |  | 2025-12-26 | [8 empty] | YES | 120 | NO
89 | IT0061 | 000 | PL |  |  |  | 73 | PIP |  | L | C | 00089 | IT0061-000-LC-00089 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | CRS | ARLNG-019-FEL2-PBO-0000-PLF-CRS-0002 | Gas Pipeline - Limay River Crossing Detail | A | 0 | INF | O | [18 empty] | 2025-12-19 |  |  | 2025-12-26 | [8 empty] | YES | 60 | NO
90 | IT0061 | 000 | PL |  |  |  | 73 | PIP |  | L | C | 00090 | IT0061-000-LC-00090 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | CRS | ARLNG-019-FEL2-PBO-0000-PLF-CRS-0003 | Gas Pipeline - State Road 22 and Channel Crossing Detail | A | 0 | INF | O | [18 empty] | 2025-12-19 |  |  | 2025-12-26 | [8 empty] | YES | 60 | NO
91 | IT0061 | 000 | PL |  |  |  | 73 | PIP |  | L | C | 00091 | IT0061-000-LC-00091 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | CRS | ARLNG-019-FEL2-PBO-0000-PLF-CRS-0001 | C3+ & C2 Pipelines - Nequen River Crossing Detail | A | 0 | INF | O | [18 empty] | 2025-12-19 |  |  | 2025-12-26 | [8 empty] | YES | 60 | NO
92 | IT0061 | 000 | PL |  |  |  | 83 | PIP |  | L | E | 00092 | IT0061-000-LE-00092 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | LST | ARLNG-019-FEL2-PBO-0000-PLF-LST-0001 | Pipeline Crossings List | A | 0 | INF | O | [18 empty] | 2025-11-14 |  |  | 2025-11-21 | [8 empty] | YES | 60 | NO
93 | IT0061 | 000 | PL |  |  |  | 84 | PIP |  | L | E | 00093 | IT0061-000-LE-00093 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | MTO | ARLNG-019-FEL2-PBO-0000-PLF-MTO-0001 | Material Take Off Pipeline | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
94 | IT0061 | 000 | PL |  |  |  | 74 | PIP |  | L | B | 00094 | IT0061-000-LB-00094 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | SPC | ARLNG-019-FEL2-PBO-0000-PLF-SPC-0002 | Line Pipe Technical Specification | A | 0 | INF | O | [18 empty] | 2025-11-14 |  |  | 2025-11-21 | [8 empty] | YES | 72 | NO
95 | IT0061 | 000 | PL |  |  |  | 75 | PIP |  | L | B | 00095 | IT0061-000-LB-00095 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | SPC | ARLNG-019-FEL2-PBO-0000-PLF-SPC-0004 | Specification for hot induction bends | A | 0 | INF | O | [18 empty] | 2025-11-14 |  |  | 2025-11-21 | [8 empty] | YES | 40 | NO
96 | IT0061 | 000 | PL |  |  |  | 77 | PIP |  | L | B | 00096 | IT0061-000-LB-00096 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | SPC | ARLNG-019-FEL2-PBO-0000-PLF-SPC-0006 | Specification for Pipeline Monolothic Isolation Joint | A | 0 | INF | O | [18 empty] | 2025-11-14 |  |  | 2025-11-21 | [8 empty] | YES | 32 | NO
97 | IT0061 | 000 | PL |  |  |  | 50 | PIP |  | L | B | 00097 | IT0061-000-LB-00097 | ARLNG | 019 | FEL2 | PBO | 0000 | STA | SPC | ARLNG-019-FEL2-PBO-0000-STA-SPC-0001 | Specification for Scraper Trap | A | 0 | INF | O | [18 empty] | 2025-11-14 |  |  | 2025-11-21 | [8 empty] | YES | 60 | NO
98 | IT0061 | 000 | PL |  |  |  | 78 | PIP |  | L | B | 00098 | IT0061-000-LB-00098 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | SPC | ARLNG-019-FEL2-PBO-0000-PLF-SPC-0005 | Specification for Pipeline Flanges & Fittings (Barred TEEs) | A | 0 | INF | O | [18 empty] | 2025-11-14 |  |  | 2025-11-21 | [8 empty] | YES | 40 | NO
99 | IT0061 | 000 | PL |  |  |  | 79 | PIP |  | L | B | 00099 | IT0061-000-LB-00099 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | SPC | ARLNG-019-FEL2-PBO-0000-PLF-SPC-0001 | Line Pipe External Coating Technical Specification | A | 0 | INF | O | [18 empty] | 2025-11-14 |  |  | 2025-11-21 | [8 empty] | YES | 40 | NO
100 | IT0061 | 000 | PL |  |  |  | 88 | PIP |  | L | B | 00100 | IT0061-000-LB-00100 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | SPC | ARLNG-019-FEL2-PBO-0000-PLF-SPC-0003 | Pipeline Field Joint Coating Specification | A | 0 | INF | O | [18 empty] | 2025-11-14 |  |  | 2025-11-21 | [8 empty] | YES | 60 | NO
101 | IT0061 | 000 | PL |  |  |  | 85 | PIP |  | L | C | 00101 | IT0061-000-LC-00101 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | CRS | ARLNG-019-FEL2-PBO-0000-PLF-CRS-0007 | Typical Pipeline RoW Cross Sections | A | 0 | INF | O | [18 empty] | 2025-11-14 |  |  | 2025-11-21 | [8 empty] | YES | 8 | NO
102 | IT0061 | 000 | PL |  |  |  | 85 | PIP |  | L | C | 00102 | IT0061-000-LC-00102 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0009 | Typical Pipeline Trench Drawing | A | 0 | INF | O | [18 empty] | 2025-11-14 |  |  | 2025-11-21 | [8 empty] | YES | 8 | NO
103 | IT0061 | 000 | PL |  |  |  | 86 | PIP |  | L | C | 00103 | IT0061-000-LC-00103 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | CRS | ARLNG-019-FEL2-PBO-0000-PLF-CRS-0011 | Typical Watercourse Crossing | A | 0 | INF | O | [18 empty] | 2025-11-14 |  |  | 2025-11-21 | [8 empty] | YES | 8 | NO
104 | IT0061 | 000 | PL |  |  |  | 86 | PIP |  | L | C | 00104 | IT0061-000-LC-00104 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | CRS | ARLNG-019-FEL2-PBO-0000-PLF-CRS-0005 | Typical Channel Crossing | A | 0 | INF | O | [18 empty] | 2025-11-14 |  |  | 2025-11-21 | [8 empty] | YES | 8 | NO
105 | IT0061 | 000 | PL |  |  |  | 86 | PIP |  | L | C | 00105 | IT0061-000-LC-00105 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | CRS | ARLNG-019-FEL2-PBO-0000-PLF-CRS-0008 | Typical Railway Crossing | A | 0 | INF | O | [18 empty] | 2025-11-14 |  |  | 2025-11-21 | [8 empty] | YES | 8 | NO
106 | IT0061 | 000 | PL |  |  |  | 86 | PIP |  | L | C | 00106 | IT0061-000-LC-00106 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | CRS | ARLNG-019-FEL2-PBO-0000-PLF-CRS-0009 | Typical State and Provincial Roads Crossing | A | 0 | INF | O | [18 empty] | 2025-11-14 |  |  | 2025-11-21 | [8 empty] | YES | 8 | NO
107 | IT0061 | 000 | PL |  |  |  | 86 | PIP |  | L | C | 00107 | IT0061-000-LC-00107 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | CRS | ARLNG-019-FEL2-PBO-0000-PLF-CRS-0010 | Typical Unpaved Road Crossing | A | 0 | INF | O | [18 empty] | 2025-11-14 |  |  | 2025-11-21 | [8 empty] | YES | 8 | NO
108 | IT0061 | 000 | PL |  |  |  | 86 | PIP |  | L | C | 00108 | IT0061-000-LC-00108 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | CRS | ARLNG-019-FEL2-PBO-0000-PLF-CRS-0004 | Typical Buried Pipe and Cable Crossing | A | 0 | INF | O | [18 empty] | 2025-11-14 |  |  | 2025-11-21 | [8 empty] | YES | 8 | NO
109 | IT0061 | 000 | PL |  |  |  | 86 | PIP |  | L | C | 00109 | IT0061-000-LC-00109 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | CRS | ARLNG-019-FEL2-PBO-0000-PLF-CRS-0006 | Typical O/h Power Line Crossing | A | 0 | INF | O | [18 empty] | 2025-11-14 |  |  | 2025-11-21 | [8 empty] | YES | 8 | NO
110 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00110 | IT0061-001-LC-00110 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0001 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 00 TO PK 09 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
111 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00111 | IT0061-001-LC-00111 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0002 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 09 TO PK 19 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
112 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00112 | IT0061-001-LC-00112 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0003 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 19 TO PK 29 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
113 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00113 | IT0061-001-LC-00113 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0004 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 29 TO PK 39 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
114 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00114 | IT0061-001-LC-00114 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0005 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 39 TO PK 49 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
115 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00115 | IT0061-001-LC-00115 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0006 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 49 TO PK 59 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
116 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00116 | IT0061-001-LC-00116 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0007 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 59 TO PK 69 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
117 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00117 | IT0061-001-LC-00117 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0008 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 69 TO PK 79 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
118 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00118 | IT0061-001-LC-00118 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0010 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 79 TO PK 89 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
119 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00119 | IT0061-001-LC-00119 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0011 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 89 TO PK 99 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
120 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00120 | IT0061-001-LC-00120 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0012 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 99 TO PK 109 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
121 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00121 | IT0061-001-LC-00121 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0013 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 109 TO PK 119 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
122 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00122 | IT0061-001-LC-00122 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0014 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 119 TO PK 129 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
123 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00123 | IT0061-001-LC-00123 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0015 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 129 TO PK 139 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
124 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00124 | IT0061-001-LC-00124 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0016 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 139 TO PK 149 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
125 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00125 | IT0061-001-LC-00125 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0017 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 149 TO PK 159 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
126 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00126 | IT0061-001-LC-00126 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0018 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 159 TO PK 169 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
127 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00127 | IT0061-001-LC-00127 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0019 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 169 TO PK 179 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
128 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00128 | IT0061-001-LC-00128 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0020 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 179 TO PK 189 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
129 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00129 | IT0061-001-LC-00129 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0021 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 189 TO PK 199 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
130 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00130 | IT0061-001-LC-00130 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0022 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 199 TO PK 209 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
131 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00131 | IT0061-001-LC-00131 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0023 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 209 TO PK 219 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
132 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00132 | IT0061-001-LC-00132 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0024 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 219 TO PK 229 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
133 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00133 | IT0061-001-LC-00133 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0025 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 229 TO PK 239 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
134 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00134 | IT0061-001-LC-00134 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0026 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 239 TO PK 249 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
135 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00135 | IT0061-001-LC-00135 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0027 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 249 TO PK 259 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
136 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00136 | IT0061-001-LC-00136 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0028 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 259 TO PK 269 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
137 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00137 | IT0061-001-LC-00137 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0029 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 269 TO PK 279 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
138 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00138 | IT0061-001-LC-00138 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0030 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 279 TO PK 289 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
139 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00139 | IT0061-001-LC-00139 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0031 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 289 TO PK 299 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
140 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00140 | IT0061-001-LC-00140 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0032 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 299 TO PK 309 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
141 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00141 | IT0061-001-LC-00141 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0033 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 309 TO PK 319 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
142 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00142 | IT0061-001-LC-00142 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0034 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 319 TO PK 329 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
143 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00143 | IT0061-001-LC-00143 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0035 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 329 TO PK 339 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
144 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00144 | IT0061-001-LC-00144 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0036 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 339 TO PK 349 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
145 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00145 | IT0061-001-LC-00145 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0037 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 349 TO PK 359 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
146 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00146 | IT0061-001-LC-00146 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0038 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 359 TO PK 369 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
147 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00147 | IT0061-001-LC-00147 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0039 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 369 TO PK 379 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
148 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00148 | IT0061-001-LC-00148 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0040 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 379 TO PK 389 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
149 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00149 | IT0061-001-LC-00149 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0041 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 389 TO PK 399 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
150 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00150 | IT0061-001-LC-00150 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0042 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 399 TO PK 409 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
151 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00151 | IT0061-001-LC-00151 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0043 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 409 TO PK 419 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
152 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00152 | IT0061-001-LC-00152 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0044 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 419 TO PK 429 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
153 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00153 | IT0061-001-LC-00153 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0045 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 429 TO PK 439 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
154 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00154 | IT0061-001-LC-00154 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0046 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 439 TO PK 449 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
155 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00155 | IT0061-001-LC-00155 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0047 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 449 TO PK 459 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
156 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00156 | IT0061-001-LC-00156 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0048 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 459 TO PK 469 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
157 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00157 | IT0061-001-LC-00157 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0049 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 469 TO PK 479 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
158 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00158 | IT0061-001-LC-00158 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0050 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 479 TO PK 489 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
159 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00159 | IT0061-001-LC-00159 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0051 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 489 TO PK 499 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
160 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00160 | IT0061-001-LC-00160 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0052 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 499 TO PK 509 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
161 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00161 | IT0061-001-LC-00161 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0053 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 509 TO PK 519 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
162 | IT0061 | 001 | PL |  |  |  | 72 | PIP |  | L | C | 00162 | IT0061-001-LC-00162 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0054 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 509 TO PK 519 | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES | 8 | NO
163 | IT0061 | 002 | PL |  |  |  | 72 | PIP |  | L | C | 00163 | IT0061-002-LC-00163 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0055 | Alignment Sheet - Condensate Pipeline to Cental Hub PK 00 TO PK 10 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
164 | IT0061 | 002 | PL |  |  |  | 72 | PIP |  | L | C | 00164 | IT0061-002-LC-00164 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0056 | Alignment Sheet - Condensate Pipeline to Cental Hub PK 10 TO PK 20 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
165 | IT0061 | 002 | PL |  |  |  | 72 | PIP |  | L | C | 00165 | IT0061-002-LC-00165 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0057 | Alignment Sheet - Condensate Pipeline to Cental Hub PK 20 TO PK 30 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
166 | IT0061 | 002 | PL |  |  |  | 72 | PIP |  | L | C | 00166 | IT0061-002-LC-00166 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0058 | Alignment Sheet - Condensate Pipeline to Cental Hub PK 30 TO PK 40 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
167 | IT0061 | 002 | PL |  |  |  | 72 | PIP |  | L | C | 00167 | IT0061-002-LC-00167 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0059 | Alignment Sheet - Condensate Pipeline to Cental Hub PK 40 TO PK 45 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
168 | IT0061 | 002 | PL |  |  |  | 72 | PIP |  | L | C | 00168 | IT0061-002-LC-00168 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0060 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 00 TO PK 10 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
169 | IT0061 | 002 | PL |  |  |  | 72 | PIP |  | L | C | 00169 | IT0061-002-LC-00169 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0061 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 10 TO PK 20 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
170 | IT0061 | 002 | PL |  |  |  | 72 | PIP |  | L | C | 00170 | IT0061-002-LC-00170 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0062 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 20 TO PK 30 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
171 | IT0061 | 002 | PL |  |  |  | 72 | PIP |  | L | C | 00171 | IT0061-002-LC-00171 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0063 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 30 TO PK 40 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
172 | IT0061 | 002 | PL |  |  |  | 72 | PIP |  | L | C | 00172 | IT0061-002-LC-00172 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0064 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 40 TO PK 50 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
173 | IT0061 | 002 | PL |  |  |  | 72 | PIP |  | L | C | 00173 | IT0061-002-LC-00173 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0065 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 50 TO PK 60 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
174 | IT0061 | 002 | PL |  |  |  | 72 | PIP |  | L | C | 00174 | IT0061-002-LC-00174 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0066 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 60 TO PK 70 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
175 | IT0061 | 002 | PL |  |  |  | 72 | PIP |  | L | C | 00175 | IT0061-002-LC-00175 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0067 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 70 TO PK 80 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
176 | IT0061 | 002 | PL |  |  |  | 72 | PIP |  | L | C | 00176 | IT0061-002-LC-00176 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0068 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 80 TO PK 90 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
177 | IT0061 | 002 | PL |  |  |  | 72 | PIP |  | L | C | 00177 | IT0061-002-LC-00177 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0069 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 90 TO PK 100 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
178 | IT0061 | 002 | PL |  |  |  | 72 | PIP |  | L | C | 00178 | IT0061-002-LC-00178 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0070 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 100 TO PK 110 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
179 | IT0061 | 002 | PL |  |  |  | 72 | PIP |  | L | C | 00179 | IT0061-002-LC-00179 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0071 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 110 TO PK 120 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
180 | IT0061 | 002 | PL |  |  |  | 72 | PIP |  | L | C | 00180 | IT0061-002-LC-00180 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0072 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 120 TO PK 130 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
181 | IT0061 | 002 | PL |  |  |  | 72 | PIP |  | L | C | 00181 | IT0061-002-LC-00181 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0073 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 130 TO PK 140 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
182 | IT0061 | 002 | PL |  |  |  | 72 | PIP |  | L | C | 00182 | IT0061-002-LC-00182 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0074 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 140 TO PK 150 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
183 | IT0061 | 002 | PL |  |  |  | 72 | PIP |  | L | C | 00183 | IT0061-002-LC-00183 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0075 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 150 TO PK 160 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
184 | IT0061 | 002 | PL |  |  |  | 72 | PIP |  | L | C | 00184 | IT0061-002-LC-00184 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0076 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 160 TO PK 170 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
185 | IT0061 | 002 | PL |  |  |  | 72 | PIP |  | L | C | 00185 | IT0061-002-LC-00185 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0077 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 170 TO PK 180 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
186 | IT0061 | 002 | PL |  |  |  | 72 | PIP |  | L | C | 00186 | IT0061-002-LC-00186 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0078 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 180 TO PK 190 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
187 | IT0061 | 002 | PL |  |  |  | 72 | PIP |  | L | C | 00187 | IT0061-002-LC-00187 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0079 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 190 TO PK 200 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
188 | IT0061 | 002 | PL |  |  |  | 72 | PIP |  | L | C | 00188 | IT0061-002-LC-00188 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0080 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 200 TO PK 203 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
189 | IT0061 | 004 | PL |  |  |  | 72 | PIP |  | L | C | 00189 | IT0061-004-LC-00189 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0081 | Alignment Sheet - C3+ Pipeline to La Calera PK 00 TO PK 10 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
190 | IT0061 | 004 | PL |  |  |  | 72 | PIP |  | L | C | 00190 | IT0061-004-LC-00190 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0082 | Alignment Sheet - C3+ Pipeline to La Calera PK 10 TO PK 20 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
191 | IT0061 | 004 | PL |  |  |  | 72 | PIP |  | L | C | 00191 | IT0061-004-LC-00191 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0083 | Alignment Sheet - C3+ Pipeline to La Calera PK 20 TO PK 30 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
192 | IT0061 | 004 | PL |  |  |  | 72 | PIP |  | L | C | 00192 | IT0061-004-LC-00192 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0084 | Alignment Sheet - C3+ Pipeline to La Calera PK 30 TO PK 40 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
193 | IT0061 | 004 | PL |  |  |  | 72 | PIP |  | L | C | 00193 | IT0061-004-LC-00193 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0085 | Alignment Sheet - C3+ Pipeline to La Calera PK 40 TO PK 44 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
194 | IT0061 | 003 | PL |  |  |  | 72 | PIP |  | L | C | 00194 | IT0061-003-LC-00194 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0086 | Alignment Sheet - C2 Pipeline to La Calera PK 00 TO PK 10 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
195 | IT0061 | 003 | PL |  |  |  | 72 | PIP |  | L | C | 00195 | IT0061-003-LC-00195 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0087 | Alignment Sheet - C2 Pipeline to La Calera PK 10 TO PK 20 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
196 | IT0061 | 003 | PL |  |  |  | 72 | PIP |  | L | C | 00196 | IT0061-003-LC-00196 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0088 | Alignment Sheet - C2 Pipeline to La Calera PK 20 TO PK 30 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
197 | IT0061 | 003 | PL |  |  |  | 72 | PIP |  | L | C | 00197 | IT0061-003-LC-00197 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0089 | Alignment Sheet - C2 Pipeline to La Calera PK 30 TO PK 40 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
198 | IT0061 | 003 | PL |  |  |  | 72 | PIP |  | L | C | 00198 | IT0061-003-LC-00198 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0090 | Alignment Sheet - C2 Pipeline to La Calera PK 40 TO PK 50 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
199 | IT0061 | 003 | PL |  |  |  | 72 | PIP |  | L | C | 00199 | IT0061-003-LC-00199 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0091 | Alignment Sheet - C2 Pipeline to La Tratayen PK 50 TO PK 60 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
200 | IT0061 | 003 | PL |  |  |  | 72 | PIP |  | L | C | 00200 | IT0061-003-LC-00200 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0092 | Alignment Sheet - C2 Pipeline to La Tratayen PK 60 TO PK 70 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
201 | IT0061 | 003 | PL |  |  |  | 72 | PIP |  | L | C | 00201 | IT0061-003-LC-00201 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0093 | Alignment Sheet - C2 Pipeline to La Tratayen PK 70 TO PK 80 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
202 | IT0061 | 003 | PL |  |  |  | 72 | PIP |  | L | C | 00202 | IT0061-003-LC-00202 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0094 | Alignment Sheet - C2 Pipeline to La Tratayen PK 80 TO PK 90 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
203 | IT0061 | 003 | PL |  |  |  | 72 | PIP |  | L | C | 00203 | IT0061-003-LC-00203 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0095 | Alignment Sheet - C2 Pipeline to La Tratayen PK 90 TO PK 100 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
204 | IT0061 | 003 | PL |  |  |  | 72 | PIP |  | L | C | 00204 | IT0061-003-LC-00204 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0096 | Alignment Sheet - C2 Pipeline to La Tratayen PK 100 TO PK 110 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
205 | IT0061 | 003 | PL |  |  |  | 72 | PIP |  | L | C | 00205 | IT0061-003-LC-00205 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0097 | Alignment Sheet - C2 Pipeline to La Tratayen PK 110 TO PK 120 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
206 | IT0061 | 003 | PL |  |  |  | 72 | PIP |  | L | C | 00206 | IT0061-003-LC-00206 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0098 | Alignment Sheet - C2 Pipeline to La Tratayen PK 120 TO PK 130 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
207 | IT0061 | 003 | PL |  |  |  | 72 | PIP |  | L | C | 00207 | IT0061-003-LC-00207 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0099 | Alignment Sheet - C2 Pipeline to La Tratayen PK 130 TO PK 140 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO
208 | IT0061 | 003 | PL |  |  |  | 72 | PIP |  | L | C | 00208 | IT0061-003-LC-00208 | ARLNG | 019 | FEL2 | PBO | 0000 | PLF | DWG | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0100 | Alignment Sheet - C2 Pipeline to La Tratayen PK 140 TO PK 150 | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES | 8 | NO