## Front Page
|  | Project and SoW description: ARGENTINA LNG Export Pipelines System |  | Company Document ID: ARLNG-019-FEL2-PBO-0000-PMG-LST-0001
Contractor Document ID: IT0061-000-ZE-00001
Vendor Document ID:
|  | Document Title: Light FEED Master Deliverables List (MDL) |  |  |  | Plant Area:
Functional Unit:
Issue Date:
|  | Facility & Sub Facility Description: |  |  |  | Sheet 1 |  | of 2
Rev.: B
ARGENTINA LNG – Export Pipelines System
Light FEED Master Deliverables List (MDL)
B |  |  | ISSUED FOR INFORMATION |  | CB |  | MR | GR
A | 2025-10-16 |  | ISSUED FOR INFORMATION |  | CB |  | MR | GR
Rev | Date |  | Description |  | Prepared by |  | Revised by | Approved by

## BNT DOCUMENT LIST
ARGENTINA LNG – Export Pipelines System
MASTER DOCUMENT REGISTER (MDR)
[5 empty] | WBS |  |  | Entities |  |  |  |  | BONATTI | [13 empty] | TRANSMITTAL OUT to CLIENT |  |  | TRANSMITTAL IN from CLIENT |  |  | TRANSMITTAL OUT to 3rd Parties |  |  | TRANSMITTAL IN from 3rd Parties |  |  | TRANSMITTAL OUT to SITE |  |  | TRANSMITTAL IN from SITE |  |  |  | IFA/IFI |  |  | FINAL APPROVAL by CLIENT |  |  | FIN |  |  | FINAL APPROVAL |  |  | PROGRESS |  |  |  | Progress Percentage
ID Counter | Project Code | Main Area | Discipline | Work Category | Activity Id | Activity Description | ORIGINAL ID | Owner | PO reference | Subject Code | Document Type | Numeric Code | BONATTI's DOCUMENT NUMBER | Plant/Project | Package Number | Project Phase | Organisation Code | Unit/Facility Code | Discipline Code | Document Type | CLIENT's DOCUMENT ID | Document Title | Latest Rev. | Int. Rev. | Latest STEP | Document Class | Transmittal Code Id | Date | Issuing Reason | Transmittal Code Id | Date | Review Code | Transmittal Code Id | Date | Issuing Reason | Transmittal Code Id | Date | Review Code | Transmittal Code Id | Date | Issuing Reason | Transmittal Code Id | Date | Review Code | Planned | Forecast | Actual | Planned | Forecast | Actual | Planned | Forecast | Actual | Planned | Forecast | Actual | Engineering Progress | Mhs | Supplier Progress | Mhs | Cumulative Planned % | Cumulative Forecast % | Cumulative Actual %
209 | IT0061 | 000 | PL |  |  |  |  | PIP |  | L | C | 00209 | IT0061-000-LC-00209 | [8 empty] | Geographic base for pipeline design (Kmz) | A | 0 | INF | O | [18 empty] | 2025-12-05 |  |  | 2025-12-12 | [8 empty] | YES |  | NO
210 | IT0061 | 005 | PR |  |  |  |  | PLA |  | A | B | 00210 | IT0061-005-AB-00210 | [8 empty] | Datasheet for TURBOGENERATOR (Compressor Station) | A | 0 | IFA | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 |  |  | 2025-12-12 |  |  | 2025-12-19 |  |  | YES |  | NO
211 | IT0061 | 006 | PR |  |  |  |  | PLA |  | A | B | 00211 | IT0061-006-AB-00211 | [8 empty] | Datasheet for TURBOGENERATOR (Central Hub) | A | 0 | IFA | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 |  |  | 2025-12-12 |  |  | 2025-12-19 |  |  | YES |  | NO
212 | IT0061 | 006 | PR |  |  |  |  | PLA |  | A | B | 00212 | IT0061-006-AB-00212 | [8 empty] | Datasheet for MAIN PUMPS (Central Hub) | A | 0 | IFA | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 |  |  | 2025-12-12 |  |  | 2025-12-19 |  |  | YES |  | NO
213 | IT0061 | 005 | PR |  |  |  |  | PLA |  | A | E | 00213 | IT0061-005-AE-00213 | [8 empty] | Utilities Summary (Compressor Station) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES |  | NO
214 | IT0061 | 006 | PR |  |  |  |  | PLA |  | A | E | 00214 | IT0061-005-AE-00214 | [8 empty] | Utilities Summary (Central Hub) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES |  | NO
213 | IT0061 | 005 | PR |  |  |  |  | PLA |  | A | E | 00213 | IT0061-005-AE-00215 | [8 empty] | Effluent and Emission Summary (Compressor Station) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES |  | NO
214 | IT0061 | 006 | PR |  |  |  |  | PLA |  | A | E | 00214 | IT0061-005-AE-00216 | [8 empty] | Effluent and Emission Summary (Central Hub) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES |  | NO
215 | IT0061 | 000 | SE |  |  |  |  | PLA |  | F | B | 00215 | IT0061-000-FB-00215 | [8 empty] | ALARP Demonstration | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES |  | NO
216 | IT0061 | 005 | MC |  |  |  |  | PLA |  | M | M | 00216 | IT0061-005-MM-00216 | [8 empty] | Material Requisition for GAS SRUBBERS (Compressor Station) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES |  | NO
217 | IT0061 | 005 | MC |  |  |  |  | PLA |  | M | M | 00217 | IT0061-005-MM-00217 | [8 empty] | Material Requisition for AIRCOOLERS (Compressor Station) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES |  | NO
218 | IT0061 | 006 | MC |  |  |  |  | PLA |  | M | M | 00218 | IT0061-006-MM-00218 | [8 empty] | Material Requisition for STORAGE TANKS (Central Hub) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES |  | NO
219 | IT0061 | 005 | MC |  |  |  |  | PLA |  | M | M | 00219 | IT0061-005-MM-00219 | [8 empty] | Material Requisition for TURBOCOMPRESSORS (Compressor Station) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES |  | NO
220 | IT0061 | 005 | MC |  |  |  |  | PLA |  | M | M | 00220 | IT0061-005-MM-00220 | [8 empty] | Material Requisition for TURBOGENERATOR (Compressor Station) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES |  | NO
221 | IT0061 | 006 | MC |  |  |  |  | PLA |  | M | M | 00221 | IT0061-006-MM-00221 | [8 empty] | Material Requisition for TURBOGENERATOR (Central Hub) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES |  | NO
222 | IT0061 | 006 | MC |  |  |  |  | PLA |  | M | M | 00222 | IT0061-006-MM-00222 | [8 empty] | Material Requisition for MAIN PUMPS (Central Hub) | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES |  | NO
223 | IT0061 | 000 | PL |  |  |  |  | PLA |  | S | M | 00223 | IT0061-000-SM-00223 | [8 empty] | Material Requisition for Pipeline Valves | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES |  | NO
224 | IT0061 | 000 | PL |  |  |  |  | PIP |  | L | M | 00224 | IT0061-000-LM-00224 | [8 empty] | Material Requisition for Pig Traps | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES |  | NO
225 | IT0061 | 000 | PL |  |  |  |  | PIP |  | L | M | 00225 | IT0061-000-LM-00225 | [8 empty] | Material Requisition for Line Pipe | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES |  | NO
226 | IT0061 | 000 | PL |  |  |  |  | PIP |  | L | M | 00226 | IT0061-000-LM-00226 | [8 empty] | Material Requisition for Hot Induced Bend | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES |  | NO
227 | IT0061 | 000 | PL |  |  |  |  | PIP |  | L | M | 00227 | IT0061-000-LM-00227 | [8 empty] | Material Requisition for Barred TEE | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES |  | NO
228 | IT0061 | 000 | PL |  |  |  |  | PIP |  | L | M | 00228 | IT0061-000-LM-00228 | [8 empty] | Material Requisition for Insulation Joint | A | 0 | INF | O | [18 empty] | 2025-11-28 |  |  | 2025-12-05 | [8 empty] | YES |  | NO