## Cover Page YPF
Weekly Project Report | [11 empty] | 2025-10-16
Proyecto: | Argentina LNG ligth FEED | [8 empty] | Cut off date: 16-10-2025
Weekly Project Management Overview | [6 empty] | Key Highlights of the Next Week
Alertas y Oportunidades
Área |  | Alerts |  |  |  | Impact |  | Action Plan | Responsible | Plan | Forecast
Ingeniería | 1
Ingeniería | 0
Ingeniería | -1
Planning Indicators |  |  |  | Project “S” Curve
% Av. Real | % Av. Prog. | M
0.9307% | 0.9307% | 0% | 0
HH Proyecto | Ganadas | Planificadas | SPI
Semanal | 85 | 85 | 1
Acumulado | 85 | 0 | 0
Comments |  |  |  |  | Reason for Deviation
The Letter of Intent (LOI) was officially signed on October 3, 2025, formalizing the commitment between the parties to initiate the project. The Effective Date was established as October 6, 2025, marking the start of contractual and initial planning activities.
The Kick-Off Meeting (KOM) was successfully held on October 7, 2025, during which the main project scope, objectives, and execution guidelines were reviewed, ensuring alignment among all teams involved.
Coordination Activities for the Site Visit (October 20–24):
  i) The Site Visit Plan was submitted via email on October 10, 2025, outlining the schedule, logistics, and specific objectives of the technical visit.
  ii) The HSE Plan Visit was conducted on October 16, 2025, focusing on verifying safety procedures and environmental compliance at the project site.
1. Conduct Site Visit according to the approved Site Visit Plan.
2. Issue the package of General Deliverables (Light FEED), including:
  Project Execution Plan (PEP)
  HSSE Management Plan
  Quality Management Plan
  Detailed Schedule
Note on D27: SJSAAVED: Se deben actualizar todas las semanas los avances. Desviación: Desv> -3%: verde -6%<Desv<-3%: amarillo Desv<-6%: rojo
Note on E30: SJSAAVED: Las HH se deben actualizar todas las semanas según informes semanales

## SUMMARY AND CURVES
|  | PROJECT | Argentina LNG Ligth FEED
|  | COMPANY | Bonatti - PUMPCO |  |  |  |  | BASE | BASE | BASE | BASE | BASE | BASE | REAL/ | REAL/ | REAL/ | REAL/ | REAL/ | REAL/
|  | CONTRACT START: | 2025-10-06 |  |  |  |  | LINE | LINE | LINE | LINE | LINE | LINE | TREND | TREND | TREND | TREND | TREND | TREND
|  | CUTOFF DATE: | 2025-10-16
|  |  | CON-012 - ARLNG MONITORING AND MEASUREMENT |  |  |  |  | 3.887% | 15.01% | 75.35% | 5.755% | 0% | 0% |  | 0.9307% | 0% | 0% | 0% | 0%
SPECIALTY | PACKAGE Weightage | Weightage | PREVIOUS AC. PROGRESS * | MONTH PROGRESS | ACTUAL AC. PROGRESS | EXPECTED PROGESS | DETOUR | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31
CONSOLIDATED ENGINEERING | 100% | 100% | 0% | 0.9307% | 0.9307% | 0.9307% | 0% | 3.887% | 18.89% | 94.25% | 100% | 100% | 100% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307%
On Shore Facilities | 100% | 100% | 0% | 0.9307% | 0.9307% | 0.9307% | 0% | 3.887% | 18.89% | 94.25% | 100% | 100% | 100% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307%
General Project Management |  | 4.38% | 0% | 21.25% | 21.25% | 21.25% | 0% | 40.94% | 43.75% | 59.69% | 100% | 100% | 100% | 21.25% | 21.25% | 21.25% | 21.25% | 21.25% | 21.25%
Process |  | 23.54% | 0% | 0% | 0% | 0% | 0% | 0% | 15.41% | 94.94% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Civil and Structure |  | 6.351% | 0% | 0% | 0% | 0% | 0% | 0% | 17.59% | 98.97% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Mechanical |  | 0.657% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Electrical |  | 7.391% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Quality Assurance & Control |  | 0.8212% | 0% | 0% | 0% | 0% | 0% | 85% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
I&C |  | 5.475% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
HSE |  | 1.85% | 0% | 0% | 0% | 0% | 0% | 37.72% | 44.38% | 91.66% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Construction |  | 2.299% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Project Planning |  | 2.464% | 0% | 0% | 0% | 0% | 0% | 28.33% | 33.33% | 33.33% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Piping |  | 6.296% | 0% | 0% | 0% | 0% | 0% | 0% | 39.13% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Process Safety Management |  | 7.665% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Pipelines and Flow lines |  | 23.04% | 0% | 0% | 0% | 0% | 0% | 0% | 29.3% | 97.86% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Architectural |  | 5.475% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Structural |  | 1.642% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Commissioning |  | 0.657% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
| * Previous advance accumulated to the cut-off date: | 2025-10-09
PROGRESS MEASUREMENT CRITERIA ACCORDING TO THE EMISSION
| QUALIFIABLE DOCUMENTS |  |  |  | % PROGRESS
| ISSUED REV. A |  |  |  | 30%
| APPROVED LETTER |  |  |  | 30%
| ISSUED REV. 0 |  |  |  | 25%
| APPROVED NUMBER |  |  |  | 15%
| INFORMATIVE DOCUMENTS |  |  |  | % PROGRESS
| ISSUED REV. A |  |  |  | 85%
| ISSUED REV. 0 |  |  |  | 15%
|  | CONTRACTOR SIGNATURE |  | YPF SIGNATURE
|  | PROJECT: | Argentina LNG Ligth FEED
|  | COMPANY: | Bonatti - PUMPCO
|  | AWARD: | 2025-10-06
|  | CUTOFF DATE: | 2025-10-16
|  | PROJECT: | Argentina LNG Ligth FEED
|  | COMPANY: | Bonatti - PUMPCO
|  | AWARD: | 2025-10-06
|  | CUTOFF DATE: | 2025-10-16
|  | PROJECT: | Argentina LNG Ligth FEED
|  | COMPANY: | Bonatti - PUMPCO
|  | AWARD: | 2025-10-06
|  | CUTOFF DATE: | 2025-10-16
|  | PROJECT: | Argentina LNG Ligth FEED
|  | COMPANY: | Bonatti - PUMPCO
|  | AWARD: | 2025-10-06
|  | CUTOFF DATE: | 2025-10-16
Formulas:
BASE = EOMONTH([BASE],1)
REAL/ = [BASE]

## LISTAS DESPLEGABLES (hidden)
X
O
Z
On Shore Facilities
General Project Management
Process
Civil and Structure
Mechanical
Electrical
Marine
I&C
Materials
HSE
Construction
Telecommunication
Piping
Special Studies
Marine channel modifications

## DATABASE AND CURVES
[6 empty] | PROJECT: | Argentina LNG Ligth FEED | [8 empty] | ISSUED Rev A |  | APPROVED LETTER | 85% | ISSUED Rev 0 |  | APR Number | 100% | BASE | BASE | BASE | BASE | BASE | BASE | BASE | BASE | BASE | BASE | BASE | BASE | BASE | BASE | BASE | BASE | BASE | BASE | BASE | BASE | BASE | BASE | BASE | BASE | BASE | BASE | REAL/ | REAL/ | REAL/ | REAL/ | REAL/ | REAL/ | REAL/ | REAL/ | REAL/ | REAL/ | REAL/ | REAL/ | REAL/ | REAL/ | REAL/ | REAL/ | REAL/ | REAL/ | REAL/ | REAL/ | REAL/ | REAL/ | REAL/ | REAL/ | REAL/ | REAL/
|  | ArLNG |  |  |  | COMPANY: | Bonatti - PUMPCO |  | C |  |  | CURRENT STATUS OF THE DOCUMENT |  | PROGRESS |  | INFORMATIVE: | 85% | INFORMATIVE: | - | INFORMATIVE: | 100% | INFORMATIVE: | - | LINE | LINE | LINE | LINE | LINE | LINE | LINE | LINE | LINE | LINE | LINE | LINE | LINE | LINE | LINE | LINE | LINE | LINE | LINE | LINE | LINE | LINE | LINE | LINE | LINE | LINE | Trend | Trend | Trend | Trend | Trend | Trend | Trend | Trend | Trend | Trend | Trend | Trend | Trend | Trend | Trend | Trend | Trend | Trend | Trend | Trend | Trend | Trend | Trend | Trend | Trend | Trend
|  | PROJECT |  |  |  | CUTOFF DATE: | 2025-10-16 |  | I | [6 empty] | QUALIFIABLE: | 30% | QUALIFIABLE: | 60% | QUALIFIABLE: | 85% | QUALIFIABLE: | 100% |  | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
CV1 | CV2 | CV3 | CV4 | CV5 | Main Code (YPF) | ACT ID | Description | SPECIALTY-PACKAGE | Classification | MH | Weightage | Actual Rev. | Actual state | PROGRESS BL | Real PROGRESS | EM Rev. A (Base line) | EM Rev. A (Real/Trend) | APPROVED LETTER (Base line) | APPROVED LETTER (Real/Trend) | EM Rev. 0 (Base line) | EM Rev. 0 (Real/Trend) | APR Number (Base line) | APR Number (Real/Trend) | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02
[5 empty] | CONSOLIDATED ENGINEERING | [5 empty] | 100% |  |  | 0.9307% | 0.9307% | 2026-01-12 | 2025-10-16 | 2026-01-19 | 0 | 2026-01-26 | 0 | 2025-12-05 | 0 | 0% | 0.9307% | 3.723% | 3.887% | 4.38% | 4.38% | 15.55% | 18.89% | 69.59% | 75.88% | 84.09% | 94.25% | 94.25% | 95.89% | 99.38% | 99.38% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307%
[5 empty] | On Shore Facilities |  |  |  |  | 9133 | 100% |  |  | 0.9307% | 0.9307% | 2026-01-12 | 2025-10-16 | 2026-01-19 | 0 | 2026-01-26 | 0 | 2025-12-05 | 0 | 0% | 0.9307% | 3.723% | 3.887% | 4.38% | 4.38% | 15.55% | 18.89% | 69.59% | 75.88% | 84.09% | 94.25% | 94.25% | 95.89% | 99.38% | 99.38% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307% | 0.9307%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PMG-LST-0001 | A1980 | Light FEED Master Deliverables List (MDL) | General Project Management | O | 100 | 1.095% |  | ISSUED Rev A | 85% | 85% | 2025-10-16 | 2025-10-16 | 2025-10-23 | - | 2025-10-30 | - | - | - | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PMG-PLN-0001 | A1990 | Light FEED PEP | General Project Management | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-10-20 | - | 2025-10-27 | - | 2025-11-03 | - | - | - | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-HSE-LYT-0001 | A2000 | Light FEED HSSE Management Plan | HSE | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-10-20 | - | 2025-10-27 | - | 2025-11-03 | - | - | - | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-QAC-PLN-0001 | A2010 | Light FEED Quality Management Plan | Quality Assurance & Control | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-10-20 | - | 2025-10-27 | - | 2025-11-03 | - | - | - | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLG-SCH-0002 | A2020 | Light FEED Detail Schedule | Project Planning | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-10-20 | - | 2025-10-27 | - | 2025-11-03 | - | - | - | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PMG-RPT-0001 | A2030 | Light FEED Close-out Report | General Project Management | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-12-19 | - | 2025-12-26 | - | 2026-01-02 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLG-CBE-0001 | A2050 | EPC Progressive Lump Sum Technical and Commercial Offer with a binding price with a maximum deviation | Project Planning | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2026-01-12 | - | 2026-01-19 | - | 2026-01-26 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PMG-SOW-0001 | A2050 | EPC Scope of Works | General Project Management | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2026-01-12 | - | 2026-01-19 | - | 2026-01-26 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PMG-PLN-0002 | A2050 | PEP EPC Phase | General Project Management | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2026-01-12 | - | 2026-01-19 | - | 2026-01-26 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PRO-PLN-0001 | A2050 | Procurement Plan for EPC phase | Process | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2026-01-12 | - | 2026-01-19 | - | 2026-01-26 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLG-SCH-0001 | A2050 | EPC Detail Schedule | Project Planning | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2026-01-12 | - | 2026-01-19 | - | 2026-01-26 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PRO-DES-0001 | A2050 | EPC Basis of Design | Process | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-12-19 | - | 2025-12-26 | - | 2026-01-02 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-HSE-RPT-0001 | A2000 | Environmental Data Book | HSE | O | 94 | 1.029% |  | No ISSUED | 0% | 0% | 2025-12-19 | - | 2025-12-26 | - | 2026-01-02 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PRO-DES-0002 | A1010 | LIGHT FEED Basis of Design for all disciplines | Process | X | 125 | 1.369% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | 2025-12-05 | - | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 60% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PRO-RPT-0001 | A1020 | Hydraulic Calculation Report (pressure profile definition, Compressor Stations number and location definition) | Process | O | 125 | 1.369% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PRO-PFD-0002 | A1030 | Process Flow Diagrams and H&MB (Compresor Station) | Process | X | 125 | 1.369% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | 2025-12-05 | - | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 60% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PRO-PFD-0001 | A1030 | Process Flow Diagrams and H&MB (Central Hub) | Process | X | 125 | 1.369% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | 2025-12-05 | - | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 60% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PRO-UFD-0002 | A1040 | Utilities Flow Diagrams (Compressor Station) | Process | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PRO-UFD-0001 | A1040 | Utilities Flow Diagrams (Central Hub) | Process | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PRO-PID-0003 | A1100 | Piping & Instrument Diagrams (Compressor Station) | Process | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PRO-PID-0002 | A1100 | Piping & Instrument Diagrams (Central Hub) | Process | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PRO-PID-0001 | A1100 | Piping & Instrument Diagrams (BVS, Scraper trap) | Process | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PRO-RPT-0005 | A1070 | Process Equipment Summary (Compressor Station) | Process | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PRO-RPT-0004 | A1070 | Process Equipment Summary (Central Hub) | Process | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PRO-TDS-0002 | A1070 | Datasheet for GAS SRUBBERS (Compressor Station) | Process | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PRO-TDS-0001 | A1070 | Datasheet for AIRCOOLERS (Compressor Station) | Process | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PRO-TDS-0003 | A1070 | Datasheet for STOREGE TANKS (Central Hub) | Process | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PRO-TDS-0004 | A1070 | Datasheet for TURBOCOMPRESSORS (Compressor Station) | Process | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PRO-CAL-0002 | A1110 | Process Equipment Calculation Note (Compressor Station) | Process | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PRO-CAL-0001 | A1110 | Process Equipment Calculation Note (Central Hub) | Process | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PRO-RPT-0003 | A1120 | Pressure relieving system calculation report (Compressor Station) | Process | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PRO-RPT-0002 | A1120 | Pressure relieving system calculation report (Central Hub) | Process | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PRO-STR-0002 | A1130 | Operation and Control Philosophy (Compressor Station) | Process | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-12-19 | - | 2025-12-26 | - | 2026-01-02 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PRO-STR-0001 | A1130 | Operation and Control Philosophy (Central Hub) | Process | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-12-19 | - | 2025-12-26 | - | 2026-01-02 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PSM-LYT-0005 | A1170 | Hazardous area classification layout (Compressor Station) | Process Safety Management | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PSM-LYT-0004 | A1170 | Hazardous area classification layout (Central Hub) | Process Safety Management | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PSM-LYT-0003 | A1170 | Hazardous area classification layout (BVS, scraper trap) | Process Safety Management | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PSM-LYT-0002 | A1190 | Firefighting Layout - network and equipment (Compressor Station) | Process Safety Management | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PSM-LYT-0001 | A1190 | Firefighting Layout - network and equipment (Central Hub) | Process Safety Management | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PSM-HAZ-0001 | A1210 | HAZID | Process Safety Management | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PSM-RPT-0001 | A1220 | EAC + ACR | Process Safety Management | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PIP-LYT-0003 | A1230 | Overall Plot Plan (Compressor Stations) | Piping | X | 125 | 1.369% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | 2025-12-05 | - | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 60% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PIP-LYT-0002 | A1230 | Overall Plot Plan (Central Hub) | Piping | X | 125 | 1.369% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | 2025-12-05 | - | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 60% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PIP-LYT-0001 | A1230 | Overall Plot Plan (BVS, scraper traps) | Piping | X | 125 | 1.369% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | 2025-12-05 | - | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 60% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-STR-0001 | A1240 | Material selection philosophy | Pipelines and Flow lines | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PIP-RPT-0001 | A1250 | Summary of the pipe classes of the project. | Piping | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PIP-TDS-0001 | A1260 | Simplified Data Sheet for Manual Valves | Piping | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-ARC-LST-0002 | A1320 | Buildings - Summary List (Compressor Station) | Architectural | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-ARC-LST-0001 | A1320 | Buildings - Summary List (Central Hub) | Architectural | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-ARC-LYT-0002 | A1330 | Buildings - General Layout -preliminary footprint and orientation (Compressor Station) | Architectural | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-ARC-LYT-0001 | A1330 | Buildings - General Layout -preliminary footprint and orientation (Central Hub) | Architectural | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-ARC-DWG-0002 | A1340 | Buildings - Architectural typical drawings (Compressor Station) | Architectural | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-ARC-DWG-0001 | A1340 | Buildings - Architectural typical drawings (Central Hub) | Architectural | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-STC-CAL-0002 | A1350 | Steel Structures - Preliminary sizing (Compressor Station) | Structural | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-STC-CAL-0001 | A1350 | Steel Structures - Preliminary sizing (Central Hub) | Structural | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-CVS-CAL-0002 | A1360 | Foundations - Preliminary sizing (Compressor Station) | Civil and Structure | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-CVS-CAL-0001 | A1360 | Foundations - Preliminary sizing (Central Hub) | Civil and Structure | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-CVS-LYT-0002 | A1370 | Foundations - Preliminary General Layout (Compressor Station) | Civil and Structure | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-CVS-LYT-0001 | A1370 | Foundations - Preliminary General Layout (Central Hub) | Civil and Structure | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-ELE-RPT-0001 | A1410 | Electrical studies (power source and availability) | Electrical | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-ELE-LST-0003 | A1420 | Electrical load list and load balance (Compressor Station) | Electrical | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-ELE-LST-0002 | A1420 | Electrical load list and load balance (Central Hub) | Electrical | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-ELE-LST-0001 | A1420 | Electrical load list and load balance (BVS, scraper trap) | Electrical | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-ELE-SLD-0003 | A1430 | Single-line diagrams (Compresso Station) | Electrical | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-ELE-SLD-0002 | A1430 | Single-line diagrams (Cental Hub) | Electrical | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-ELE-SLD-0001 | A1430 | Single-line diagrams (BVS, scraper trap) | Electrical | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-INS-DWG-0003 | A1510 | Control system architecture, safety, F&G and other systems (Overall) | I&C | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-INS-DWG-0002 | A1510 | Control system architecture, safety, F&G and other systems (Compressor Station) | I&C | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-INS-DWG-0001 | A1510 | Control system architecture, safety, F&G and other systems (Central Hub) | I&C | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-INS-SPC-0002 | A1520 | Technical Specification of Integrated Control and Safety System (ICSS) Design (Including DCS, SIS and FGS) | I&C | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-INS-SPC-0001 | A1520 | Technical Specification of Custody Metering | I&C | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-SPC-0007 | A1540 | Specification for pipeline valves | Pipelines and Flow lines | O | 100 | 1.095% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-CON-RPT-0001 | A2050 | Constructability & Logistics Preliminary Study | Construction | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-12-19 | - | 2025-12-26 | - | 2026-01-02 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-CON-STR-0001 | A2050 | EPC execution strategy (nbr. of spreads, main equipment) | Construction | O | 75 | 0.8212% |  | No ISSUED | 0% | 0% | 2025-12-19 | - | 2025-12-26 | - | 2026-01-02 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-CON-STR-0002 | A1940 | Strategy for hydraulic test, dimensional control and drying | Construction | O | 60 | 0.657% |  | No ISSUED | 0% | 0% | 2025-12-19 | - | 2025-12-26 | - | 2026-01-02 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DGM-0001 | A1630 | Overall Pipeline schematic diagram | Pipelines and Flow lines | X | 48 | 0.5256% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | 2025-12-05 | - | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 60% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DES-0001 | A1640 | Design Criteria for pipelines | Pipelines and Flow lines | X | 80 | 0.8759% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | 2025-12-05 | - | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 60% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DES-0002 | A1650 | Pipeline Cathodic Protection Basis of Design | Pipelines and Flow lines | X | 80 | 0.8759% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | 2025-12-05 | - | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 60% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-CMM-STR-0001 | A1930 | Pipeline pre-Commissioning and Commissioning Philosophy | Commissioning | O | 60 | 0.657% |  | No ISSUED | 0% | 0% | 2025-12-19 | - | 2025-12-26 | - | 2026-01-02 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-CVS-RPT-0002 | A1800 | Geotechnical Investigation - Scope of Work for LIGHT FEED soil investigation analysis | Civil and Structure | O | 40 | 0.438% |  | No ISSUED | 0% | 0% | 2025-12-19 | - | 2025-12-26 | - | 2026-01-02 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-CVS-RPT-0001 | A1830 | Geotechnical Investigation - Data interpretation Report (desktop study) | Civil and Structure | O | 80 | 0.8759% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-CVS-RPT-0003 | A1840 | Topographic Survey - Scope of Work and Technical Requirements for LIGHT FEED | Civil and Structure | O | 40 | 0.438% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-RPT-0003 | A1660 | Pipelines Thickness Calculation and Selection Report | Pipelines and Flow lines | O | 60 | 0.657% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-RPT-0001 | A1670 | Buoyancy Calculation Report | Pipelines and Flow lines | O | 60 | 0.657% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-PLN-0001 | A1810 | Overall Pipelines Route Plan | Pipelines and Flow lines | X | 60 | 0.657% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | 2025-12-05 | - | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 60% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-CVS-DWG-0001 | A1850 | Access roads and circulation plan (based on .kmz) | Civil and Structure | O | 60 | 0.657% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-CVS-PLN-0001 | A1860 | Earthworks - Preliminary Soil Movement Plan | Civil and Structure | O | 60 | 0.657% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-RPT-0002 | A1920 | Special Crossings Design report | Pipelines and Flow lines | O | 120 | 1.314% |  | No ISSUED | 0% | 0% | 2025-12-19 | - | 2025-12-26 | - | 2026-01-02 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-CRS-0002 | A1920 | Gas Pipeline - Limay River Crossing Detail | Pipelines and Flow lines | O | 60 | 0.657% |  | No ISSUED | 0% | 0% | 2025-12-19 | - | 2025-12-26 | - | 2026-01-02 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-CRS-0003 | A1920 | Gas Pipeline - State Road 22 and Channel Crossing Detail | Pipelines and Flow lines | O | 60 | 0.657% |  | No ISSUED | 0% | 0% | 2025-12-19 | - | 2025-12-26 | - | 2026-01-02 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-CRS-0001 | A1920 | C3+ & C2 Pipelines - Nequen River Crossing Detail | Pipelines and Flow lines | O | 60 | 0.657% |  | No ISSUED | 0% | 0% | 2025-12-19 | - | 2025-12-26 | - | 2026-01-02 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-LST-0001 | A1820 | Pipeline Crossings List | Pipelines and Flow lines | O | 60 | 0.657% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-MTO-0001 | A1870 | Material Take Off Pipeline | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-SPC-0002 | A1690 | Line Pipe Technical Specification | Pipelines and Flow lines | O | 72 | 0.7883% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-SPC-0004 | A1710 | Specification for hot induction bends | Pipelines and Flow lines | O | 40 | 0.438% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-SPC-0006 | A1770 | Specification for Pipeline Monolothic Isolation Joint | Pipelines and Flow lines | O | 32 | 0.3504% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-STA-SPC-0001 | A1750 | Specification for Scraper Trap | Mechanical | O | 60 | 0.657% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-SPC-0005 | A1730 | Specification for Pipeline Flanges & Fittings (Barred TEEs) | Pipelines and Flow lines | O | 40 | 0.438% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-SPC-0001 | A1790 | Line Pipe External Coating Technical Specification | Pipelines and Flow lines | O | 40 | 0.438% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-SPC-0003 | A1790 | Pipeline Field Joint Coating Specification | Pipelines and Flow lines | O | 60 | 0.657% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-CRS-0007 | A1680 | Typical Pipeline RoW Cross Sections | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0009 | A1680 | Typical Pipeline Trench Drawing | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-CRS-0011 | A1680 | Typical Watercourse Crossing | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-CRS-0005 | A1680 | Typical Channel Crossing | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-CRS-0008 | A1680 | Typical Railway Crossing | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-CRS-0009 | A1680 | Typical State and Provincial Roads Crossing | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-CRS-0010 | A1680 | Typical Unpaved Road Crossing | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-CRS-0004 | A1680 | Typical Buried Pipe and Cable Crossing | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-CRS-0006 | A1680 | Typical O/h Power Line Crossing | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-14 | - | 2025-11-21 | - | 2025-11-28 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0001 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 00 TO PK 09 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0002 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 09 TO PK 19 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0003 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 19 TO PK 29 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0004 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 29 TO PK 39 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0005 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 39 TO PK 49 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0006 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 49 TO PK 59 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0007 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 59 TO PK 69 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0008 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 69 TO PK 79 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0010 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 79 TO PK 89 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0011 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 89 TO PK 99 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0012 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 99 TO PK 109 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0013 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 109 TO PK 119 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0014 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 119 TO PK 129 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0015 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 129 TO PK 139 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0016 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 139 TO PK 149 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0017 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 149 TO PK 159 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0018 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 159 TO PK 169 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0019 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 169 TO PK 179 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0020 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 179 TO PK 189 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0021 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 189 TO PK 199 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0022 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 199 TO PK 209 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0023 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 209 TO PK 219 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0024 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 219 TO PK 229 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0025 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 229 TO PK 239 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0026 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 239 TO PK 249 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0027 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 249 TO PK 259 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0028 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 259 TO PK 269 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0029 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 269 TO PK 279 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0030 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 279 TO PK 289 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0031 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 289 TO PK 299 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0032 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 299 TO PK 309 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0033 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 309 TO PK 319 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0034 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 319 TO PK 329 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0035 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 329 TO PK 339 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0036 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 339 TO PK 349 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0037 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 349 TO PK 359 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0038 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 359 TO PK 369 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0039 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 369 TO PK 379 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0040 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 379 TO PK 389 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0041 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 389 TO PK 399 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0042 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 399 TO PK 409 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0043 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 409 TO PK 419 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0044 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 419 TO PK 429 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0045 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 429 TO PK 439 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0046 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 439 TO PK 449 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0047 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 449 TO PK 459 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0048 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 459 TO PK 469 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0049 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 469 TO PK 479 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0050 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 479 TO PK 489 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0051 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 489 TO PK 499 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0052 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 499 TO PK 509 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0053 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 509 TO PK 519 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0054 | A1880 | Alignment Sheet - Gas Pipeline to Sierra Grande PK 509 TO PK 519 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-11-28 | - | 2025-12-05 | - | 2025-12-12 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0055 | A1890 | Alignment Sheet - Condensate Pipeline to Cental Hub PK 00 TO PK 10 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0056 | A1890 | Alignment Sheet - Condensate Pipeline to Cental Hub PK 10 TO PK 20 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0057 | A1890 | Alignment Sheet - Condensate Pipeline to Cental Hub PK 20 TO PK 30 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0058 | A1890 | Alignment Sheet - Condensate Pipeline to Cental Hub PK 30 TO PK 40 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0059 | A1890 | Alignment Sheet - Condensate Pipeline to Cental Hub PK 40 TO PK 45 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0060 | A1890 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 00 TO PK 10 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0061 | A1890 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 10 TO PK 20 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0062 | A1890 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 20 TO PK 30 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0063 | A1890 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 30 TO PK 40 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0064 | A1890 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 40 TO PK 50 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0065 | A1890 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 50 TO PK 60 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0066 | A1890 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 60 TO PK 70 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0067 | A1890 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 70 TO PK 80 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0068 | A1890 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 80 TO PK 90 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0069 | A1890 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 90 TO PK 100 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0070 | A1890 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 100 TO PK 110 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0071 | A1890 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 110 TO PK 120 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0072 | A1890 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 120 TO PK 130 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0073 | A1890 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 130 TO PK 140 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0074 | A1890 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 140 TO PK 150 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0075 | A1890 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 150 TO PK 160 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0076 | A1890 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 160 TO PK 170 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0077 | A1890 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 170 TO PK 180 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0078 | A1890 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 180 TO PK 190 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0079 | A1890 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 190 TO PK 200 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0080 | A1890 | Alignment Sheet - Condensate Pipeline to CABO VMOS PK 200 TO PK 203 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0081 | A1910 | Alignment Sheet - C3+ Pipeline to La Calera PK 00 TO PK 10 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0082 | A1910 | Alignment Sheet - C3+ Pipeline to La Calera PK 10 TO PK 20 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0083 | A1910 | Alignment Sheet - C3+ Pipeline to La Calera PK 20 TO PK 30 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0084 | A1910 | Alignment Sheet - C3+ Pipeline to La Calera PK 30 TO PK 40 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0085 | A1910 | Alignment Sheet - C3+ Pipeline to La Calera PK 40 TO PK 44 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0086 | A1900 | Alignment Sheet - C2 Pipeline to La Calera PK 00 TO PK 10 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0087 | A1900 | Alignment Sheet - C2 Pipeline to La Calera PK 10 TO PK 20 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0088 | A1900 | Alignment Sheet - C2 Pipeline to La Calera PK 20 TO PK 30 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0089 | A1900 | Alignment Sheet - C2 Pipeline to La Calera PK 30 TO PK 40 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0090 | A1900 | Alignment Sheet - C2 Pipeline to La Calera PK 40 TO PK 50 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0091 | A1900 | Alignment Sheet - C2 Pipeline to La Tratayen PK 50 TO PK 60 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0092 | A1900 | Alignment Sheet - C2 Pipeline to La Tratayen PK 60 TO PK 70 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0093 | A1900 | Alignment Sheet - C2 Pipeline to La Tratayen PK 70 TO PK 80 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0094 | A1900 | Alignment Sheet - C2 Pipeline to La Tratayen PK 80 TO PK 90 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0095 | A1900 | Alignment Sheet - C2 Pipeline to La Tratayen PK 90 TO PK 100 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0096 | A1900 | Alignment Sheet - C2 Pipeline to La Tratayen PK 100 TO PK 110 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0097 | A1900 | Alignment Sheet - C2 Pipeline to La Tratayen PK 110 TO PK 120 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0098 | A1900 | Alignment Sheet - C2 Pipeline to La Tratayen PK 120 TO PK 130 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0099 | A1900 | Alignment Sheet - C2 Pipeline to La Tratayen PK 130 TO PK 140 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | ARLNG-019-FEL2-PBO-0000-PLF-DWG-0100 | A1900 | Alignment Sheet - C2 Pipeline to La Tratayen PK 140 TO PK 150 | Pipelines and Flow lines | O | 8 | 0.08759% |  | No ISSUED | 0% | 0% | 2025-12-05 | - | 2025-12-12 | - | 2025-12-19 | - | - | - | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%

## INDICADORES
| Proyecto: | Argentina LNG ligth FEED |  | Engineering Progress Summary | [10 empty] | Report Date
| Codigo: | IVL-73
| Contratista: | Bonatti Pumpco | [12 empty] | 2025-10-16
Document Issuance Status
[5 empty] | Issue in Words |  |  |  |  | Issue in Number | [5 empty] | Letter |  | Number
| Original Total | Cancelled | New to the Base | Current Total | Planned | Total Issued | Issued as Planned | Issued Ahead of Schedule | Issued Delayed | Planned | Total Issued | Issued as Planned | Issued Ahead of Schedule | Issued Delayed |  | % Issuance | % Schedule Compliance | % Issuance | % Schedule Compliance
Emisión de Documentos | 208 |  |  |  | 1 | 1 | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 |  | 1 | 1
General Project Management | 5 |  |  |  | 1 | 1 | 1 | 1 | [7 empty] | 100% | 100%
Process | 23
Civil and Structure | 9
Mechanical | 1
Electrical | 7
Quality Assurance & Control | 1
I&C | 5
HSE | 2
Construction | 3
Project Planning | 3
Piping | 5
Process Safety Management | 7
Pipelines and Flow lines | 128
Architectural | 6
Structural | 2
Commissioning | 1

## COMMUNICATION LOG
Weekly Project Report
Argentina LNG ligth FEED
Communication Log
[7 empty] | Issued By |  |  |  | Response
Internal Document Code | Client Document Code | Rev | Discipline | Title | Code | Issue Date | Name | Company | Requires Response |  | Correlative | Delivery Date | Channel | Observation
[9 empty] | YES | NO
IT0061-000-ZE-00001 | ARLNG-019-FEL2-PBO-0000-PMG-LST-0001 | A | Project Management | Light FEED Master Deliverables List (MDL) | INF | 2025-10-16 | Cintia Bini | Bonatti | X |  |  |  |  | Pending Response

## Sheet1 (hidden)
YD-3GyE06.15-01-GE-PR-LP-0004 | 2016-07-27 | 0 | 2016-07-27 | YD-3GyE06.15-01-GE-PR-LP-0004 |  |  | 2016-07-29 | 0 | 2016-07-29
YD-3GyE06.15-01-GE-PR-PI-0011 | 2016-07-29 | 0 | 2016-07-29 | YD-3GyE06.15-01-GE-PR-PI-0011 | 2016-08-14 | 2016-08-14 | 2016-08-23 | 0 | 2016-08-23
YD-3GyE06.15-01-GE-PR-MD-0022 | 2016-07-29 | 0 | 2016-07-29 | YD-3GyE06.15-01-GE-PR-MD-0022 | 2016-08-14 | 2016-08-14 | 2016-08-23 | 0 | 2016-08-23
YD-3GyE06.15-01-GE-PR-MD-0027 | 2016-07-28 | 0 | 2016-07-28 | YD-3GyE06.15-01-GE-PR-MD-0027 |  |  | 2016-07-29 | 0 | 2016-07-29
YD-3GyE06.15-01-GE-PR-MD-0031 | 2016-07-28 | 0 | 2016-07-28 | YD-3GyE06.15-01-GE-PR-MD-0031 |  |  | 2016-07-29 | 0 | 2016-07-29
YD-3GyE06.15-01-GE-PR-MD-0034 | 2016-07-28 | 0 | 2016-07-28 | YD-3GyE06.15-01-GE-PR-MD-0034 |  |  | 2016-07-29 | 0 | 2016-07-29
YD-3GyE06.15-01-GE-CI-PL-0039 | 2016-07-07 | 0 | 2016-07-07 | YD-3GyE06.15-01-GE-CI-PL-0039 |  |  | 2016-07-07 | 0 | 2016-07-07
YD-3GyE06.15-01-GE-CI-PL-0040 | 2016-07-07 | 0 | 2016-07-07 | YD-3GyE06.15-01-GE-CI-PL-0040 |  |  | 2016-07-07 | 0 | 2016-07-07
YD-3GyE06.15-01-GE-CI-PL-0041 | 2016-07-07 | 0 | 2016-07-07 | YD-3GyE06.15-01-GE-CI-PL-0041 |  |  | 2016-07-07 | 0 | 2016-07-07
YD-3GyE06.15-01-GE-CI-PL-0042 | 2016-07-07 | 0 | 2016-07-07 | YD-3GyE06.15-01-GE-CI-PL-0042 |  |  | 2016-07-07 | 0 | 2016-07-07
YD-3GyE06.15-01-GE-CI-MC-0060 | 2016-07-01 | -3 | 2016-07-04 | YD-3GyE06.15-01-GE-CI-MC-0060 |  |  | 2016-07-04 | 0 | 2016-07-04
YD-3GyE06.15-01-GE-CI-DH-0065 | 2016-07-01 | -3 | 2016-07-04 | YD-3GyE06.15-01-GE-CI-DH-0065 |  |  | 2016-07-04 | 0 | 2016-07-04
YD-3GyE06.15-01-GE-CI-PL-0099 | 2016-07-12 | 0 | 2016-07-12 | YD-3GyE06.15-01-GE-CI-PL-0099 |  |  | 2016-07-12 | 0 | 2016-07-12
YD-3GyE06.15-01-GE-CI-DH-0101 | 2016-07-12 | 0 | 2016-07-12 | YD-3GyE06.15-01-GE-CI-DH-0101 |  |  | 2016-07-12 | 0 | 2016-07-12
YD-3GyE06.15-01-GE-CI-MC-0114 | 2016-07-29 | 0 | 2016-07-29 | YD-3GyE06.15-01-GE-CI-MC-0114 |  |  | 2016-07-29 | 0 | 2016-07-29
YD-3GyE06.15-01-GE-CI-PL-0130 | 2016-07-12 | 0 | 2016-07-12 | YD-3GyE06.15-01-GE-CI-PL-0130 |  |  | 2016-07-12 | 0 | 2016-07-12
YD-3GyE06.15-01-GE-CI-DH-0132 | 2016-07-12 | 0 | 2016-07-12 | YD-3GyE06.15-01-GE-CI-DH-0132 |  |  | 2016-07-12 | 0 | 2016-07-12
YD-3GyE06.15-01-GE-CI-PL-0142 | 2016-07-07 | 0 | 2016-07-07 | YD-3GyE06.15-01-GE-CI-PL-0142 |  |  | 2016-07-07 | 0 | 2016-07-07
YD-3GyE06.15-01-GE-CI-DH-0144 | 2016-07-07 | 0 | 2016-07-07 | YD-3GyE06.15-01-GE-CI-DH-0144 |  |  | 2016-07-07 | 0 | 2016-07-07
YD-3GyE06.15-01-GE-CI-MC-0153 | 2016-07-29 | 0 | 2016-07-29 | YD-3GyE06.15-01-GE-CI-MC-0153 |  |  | 2016-07-29 | 0 | 2016-07-29
YD-3GyE06.15-01-GE-CI-PL-0154 | 2016-07-14 | 0 | 2016-07-14 | YD-3GyE06.15-01-GE-CI-PL-0154 |  |  | 2016-07-14 | 0 | 2016-07-14
YD-3GyE06.15-01-GE-CI-DH-0156 | 2016-07-14 | 0 | 2016-07-14 | YD-3GyE06.15-01-GE-CI-DH-0156 |  |  | 2016-07-14 | 0 | 2016-07-14
YD-3GyE06.15-01-GE-CI-PL-0214 | 2016-07-29 | 0 | 2016-07-29 | YD-3GyE06.15-01-GE-CI-PL-0214 |  |  | 2016-07-29 | 0 | 2016-07-29
YD-3GyE06.15-01-GE-CI-PL-0215 | 2016-07-29 | 0 | 2016-07-29 | YD-3GyE06.15-01-GE-CI-PL-0215 |  |  | 2016-07-29 | 0 | 2016-07-29
YD-3GyE06.15-01-GE-EQ-PL-0005 | 2016-07-28 | 0 | 2016-07-28 | YD-3GyE06.15-01-GE-EQ-PL-0005 |  |  | 2016-07-29 | 0 | 2016-07-29
YD-3GyE06.15-01-GE-EQ-HD-0025 | 2016-07-28 | 0 | 2016-07-28 | YD-3GyE06.15-01-GE-EQ-HD-0025 |  |  | 2016-07-29 | 0 | 2016-07-29
YD-3GyE06.15-01-GE-EQ-PL-0026 | 2016-07-28 | 0 | 2016-07-28 | YD-3GyE06.15-01-GE-EQ-PL-0026 |  |  | 2016-07-29 | 0 | 2016-07-29
YD-3GyE06.15-01-GE-EM-HD-0019 | 2016-07-29 | 0 | 2016-07-29 | YD-3GyE06.15-01-GE-EM-HD-0019 |  |  | 2016-07-29 | 0 | 2016-07-29
YD-3GyE06.15-01-GE-EM-RI-0020 | 2016-07-29 | 0 | 2016-07-29 | YD-3GyE06.15-01-GE-EM-RI-0020 |  |  | 2016-07-29 | 0 | 2016-07-29
YD-3GyE06.15-01-GE-EM-HD-0021 | 2016-07-26 | 0 | 2016-07-26 | YD-3GyE06.15-01-GE-EM-HD-0021 |  |  | 2016-07-26 | 0 | 2016-07-26
YD-3GyE06.15-01-GE-EM-HD-0034 | 2016-07-26 | 0 | 2016-07-26 | YD-3GyE06.15-01-GE-EM-HD-0034 |  |  | 2016-07-26 | 0 | 2016-07-26
YD-3GyE06.15-01-GE-EQ-HD-0041 | 2016-07-01 | -3 | 2016-07-04 | YD-3GyE06.15-01-GE-EQ-HD-0041 |  |  | 2016-07-04 | 0 | 2016-07-04
YD-3GyE06.15-01-GE-EQ-PL-0042 | 2016-07-04 | 0 | 2016-07-04 | YD-3GyE06.15-01-GE-EQ-PL-0042 |  |  | 2016-07-04 | 0 | 2016-07-04
YD-3GyE06.15-01-GE-EM-LM-0078 | 2016-07-12 | 0 | 2016-07-12 | YD-3GyE06.15-01-GE-EM-LM-0078 |  |  | 2016-07-12 | 0 | 2016-07-12
YD-3GyE06.16-01-GE-EM-MD-0080 | 2016-07-05 | 0 | 2016-07-05 | YD-3GyE06.16-01-GE-EM-MD-0080 | 2016-07-26 | 2016-07-26 | 2016-07-28 | 0 | 2016-07-28
YD-3GyE06.16-01-GE-EM-HD-0082 | 2016-07-29 | 0 | 2016-07-29 | YD-3GyE06.16-01-GE-EM-HD-0082 |  |  | 2016-07-29 | 0 | 2016-07-29
YD-3GyE06.15-01-GE-EM-HD-0085 | 2016-07-26 | 0 | 2016-07-26 | YD-3GyE06.15-01-GE-EM-HD-0085 |  |  | 2016-07-26 | 0 | 2016-07-26
YD-3GyE06.16-01-GE-EM-HD-0086 | 2016-07-26 | 0 | 2016-07-26 | YD-3GyE06.16-01-GE-EM-HD-0086 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 0 | 2016-07-26
YD-3GyE06.15-01-GE-EL-DU-0006 | 2016-07-07 | 0 | 2016-07-07 | YD-3GyE06.15-01-GE-EL-DU-0006 |  |  | 2016-07-07 | 0 | 2016-07-07
YD-3GyE06.15-01-GE-EL-MC-0009 | 2016-07-29 | 0 | 2016-07-29 | YD-3GyE06.15-01-GE-EL-MC-0009 |  |  | 2016-07-29 | 0 | 2016-07-29
YD-3GyE06.15-01-GE-EL-MC-0010 | 2016-07-29 | 0 | 2016-07-29 | YD-3GyE06.15-01-GE-EL-MC-0010 | 2016-08-14 | 2016-08-14 | 2016-09-06 | 0 | 2016-09-06
YD-3GyE06.15-01-GE-EL-DU-0018 | 2016-07-01 | -3 | 2016-07-04 | YD-3GyE06.15-01-GE-EL-DU-0018 |  |  | 2016-07-04 | 0 | 2016-07-04
YD-3GyE06.15-01-GE-EL-ET-0019 | 2016-07-25 | -1 | 2016-07-26 | YD-3GyE06.15-01-GE-EL-ET-0019 |  |  | 2016-07-26 | 0 | 2016-07-26
YD-3GyE06.15-01-GE-EL-ET-0026 | 2016-07-07 | 0 | 2016-07-07 | YD-3GyE06.15-01-GE-EL-ET-0026 | 2016-07-22 | 2016-07-22 | 2016-09-30 | 0 | 2016-09-30
YD-3GyE06.15-01-GE-EL-MC-0029 | 2016-07-29 | 0 | 2016-07-29 | YD-3GyE06.15-01-GE-EL-MC-0029 |  |  | 2016-07-29 | 0 | 2016-07-29
YD-3GyE06.15-01-GE-EL-MC-0033 | 2016-07-29 | 0 | 2016-07-29 | YD-3GyE06.15-01-GE-EL-MC-0033 |  |  | 2016-07-29 | 0 | 2016-07-29
YD-3GyE06.15-01-GE-EL-PL-0035 | 2016-07-29 | 0 | 2016-07-29 | YD-3GyE06.15-01-GE-EL-PL-0035 |  |  | 2016-07-29 | 0 | 2016-07-29
YD-3GyE06.15-01-GE-EL-PL-0037 | 2016-07-29 | 0 | 2016-07-29 | YD-3GyE06.15-01-GE-EL-PL-0037 |  |  | 2016-07-29 | 0 | 2016-07-29
YD-3GyE06.15-01-GE-EL-PL-0041 | 2016-07-29 | 0 | 2016-07-29 | YD-3GyE06.15-01-GE-EL-PL-0041 |  |  | 2016-07-29 | 0 | 2016-07-29
YD-3GyE06.15-01-GE-EL-PL-0042 | 2016-07-29 | 0 | 2016-07-29 | YD-3GyE06.15-01-GE-EL-PL-0042 |  |  | 2016-07-29 | 0 | 2016-07-29
YD-3GyE06.15-01-GE-EL-DC-0043 | 2016-07-29 | 0 | 2016-07-29 | YD-3GyE06.15-01-GE-EL-DC-0043 |  |  | 2016-07-29 | 0 | 2016-07-29
YD-3GyE06.15-01-GE-EL-LM-0055 | 2016-07-14 | 0 | 2016-07-14 | YD-3GyE06.15-01-GE-EL-LM-0055 |  |  | 2016-07-14 | 0 | 2016-07-14
YD-3GyE06.15-01-GE-EL-PL-0104 | 2016-07-15 | 0 | 2016-07-15 | YD-3GyE06.15-01-GE-EL-PL-0104 | 2016-10-05 | 2016-10-05 | 2016-10-15 | 0 | 2016-10-15
YD-3GyE06.15-01-GE-EL-PL-0105 | 2016-07-29 | 0 | 2016-07-29 | YD-3GyE06.15-01-GE-EL-PL-0105 |  |  | 2016-07-29 | 0 | 2016-07-29
YD-3GyE06.15-01-GE-EL-PL-0107 | 2016-07-29 | 0 | 2016-07-29 | YD-3GyE06.15-01-GE-EL-PL-0107 |  |  | 2016-07-29 | 0 | 2016-07-29
YD-3GyE06.15-01-GE-EL-PL-0111 | 2016-07-15 | -3 | 2016-07-18 | YD-3GyE06.15-01-GE-EL-PL-0111 |  |  | 2016-07-18 | 0 | 2016-07-18
YD-3GyE06.15-01-GE-EL-PL-0112 | 2016-07-15 | -3 | 2016-07-18 | YD-3GyE06.15-01-GE-EL-PL-0112 |  |  | 2016-07-18 | 0 | 2016-07-18
YD-3GyE06.15-01-GE-EL-MC-0115 | 2016-07-14 | 0 | 2016-07-14 | YD-3GyE06.15-01-GE-EL-MC-0115 |  |  | 2016-07-14 | 0 | 2016-07-14
YD-3GyE06.15-01-GE-EL-ET-0121 | 2016-07-15 | -3 | 2016-07-18 | YD-3GyE06.15-01-GE-EL-ET-0121 |  |  | 2016-07-18 | 0 | 2016-07-18
YD-3GyE06.15-01-GE-EL-ET-0124 | 2016-07-29 | 0 | 2016-07-29 | YD-3GyE06.15-01-GE-EL-ET-0124 |  |  | 2016-07-29 | 0 | 2016-07-29
YD-3GyE06.15-01-GE-EL-PL-0140 | 2016-07-14 | 0 | 2016-07-14 | YD-3GyE06.15-01-GE-EL-PL-0140 |  |  | 2016-07-14 | 0 | 2016-07-14
YD-3GyE06.15-01-GE-IN-HD-0006 | 2016-07-26 | 0 | 2016-07-26 | YD-3GyE06.15-01-GE-IN-HD-0006 |  |  | 2016-07-26 | 0 | 2016-07-26
YD-3GyE06.15-01-GE-IN-HD-0007 | 2016-07-26 | 0 | 2016-07-26 | YD-3GyE06.15-01-GE-IN-HD-0007 |  |  | 2016-07-26 | 0 | 2016-07-26
YD-3GyE06.15-01-GE-IN-HD-0008 | 2016-07-26 | 0 | 2016-07-26 | YD-3GyE06.15-01-GE-IN-HD-0008 |  |  | 2016-07-26 | 0 | 2016-07-26
YD-3GyE06.15-01-GE-IN-HD-0009 | 2016-07-26 | 0 | 2016-07-26 | YD-3GyE06.15-01-GE-IN-HD-0009 |  |  | 2016-07-26 | 0 | 2016-07-26
YD-3GyE06.15-01-GE-IN-HD-0010 | 2016-07-26 | 0 | 2016-07-26 | YD-3GyE06.15-01-GE-IN-HD-0010 |  |  | 2016-07-26 | 0 | 2016-07-26
YD-3GyE06.15-01-GE-IN-HD-0011 | 2016-07-26 | 0 | 2016-07-26 | YD-3GyE06.15-01-GE-IN-HD-0011 |  |  | 2016-07-26 | 0 | 2016-07-26
YD-3GyE06.15-01-GE-IN-HD-0013 | 2016-07-26 | 0 | 2016-07-26 | YD-3GyE06.15-01-GE-IN-HD-0013 |  |  | 2016-07-26 | 0 | 2016-07-26
YD-3GyE06.15-01-GE-IN-HD-0014 | 2016-07-26 | 0 | 2016-07-26 | YD-3GyE06.15-01-GE-IN-HD-0014 |  |  | 2016-07-26 | 0 | 2016-07-26
YD-3GyE06.15-01-GE-IN-HD-0015 | 2016-07-26 | 0 | 2016-07-26 | YD-3GyE06.15-01-GE-IN-HD-0015 |  |  | 2016-07-26 | 0 | 2016-07-26
YD-3GyE06.15-01-GE-IN-HD-0016 | 2016-07-26 | 0 | 2016-07-26 | YD-3GyE06.15-01-GE-IN-HD-0016 |  |  | 2016-07-26 | 0 | 2016-07-26
YD-3GyE06.15-01-GE-IN-HD-0040 | 2016-07-01 | -3 | 2016-07-04 | YD-3GyE06.15-01-GE-IN-HD-0040 |  |  | 2016-07-04 | 0 | 2016-07-04
YD-3GyE06.15-01-GE-PI-MD-0004 | 2016-07-01 | -3 | 2016-07-04 | YD-3GyE06.15-01-GE-PI-MD-0004 |  |  | 2016-07-04 | 0 | 2016-07-04
YD-3GyE06.15-01-GE-PI-PL-0005 | 2016-07-01 | -3 | 2016-07-04 | YD-3GyE06.15-01-GE-PI-PL-0005 |  |  | 2016-07-04 | 0 | 2016-07-04
YD-3GyE06.15-01-GE-PI-PL-0014 | 2016-07-30 | 0 | 2016-07-30 | YD-3GyE06.15-01-GE-PI-PL-0014 | 2016-09-14 | 2016-09-14 | 2016-09-11 | 0 | 2016-09-11
YD-3GyE06.15-01-GE-PI-PL-0018 | 2016-07-01 | 0 | 2016-07-01 | YD-3GyE06.15-01-GE-PI-IS-0018 | 2016-10-05 | 2016-10-05 | 2016-10-15 | 0 | 2016-10-15
YD-3GyE06.15-01-GE-PI-PL-0019 | 2016-07-01 | 0 | 2016-07-01 | YD-3GyE06.15-01-GE-PI-RI-0019 | 2016-10-05 | 2016-10-05 | 2016-10-15 | 0 | 2016-10-15

## EXPLANATION (hidden)
CON-012 - ARLNG MONITORING AND MEASUREMENT
PURPOSE OF EACH FLAP:
SUMMARY AND CURVES: Shows the general status of the project. Used for certificate support.
DATABASE AND CURVES: Progress tracking sheet for each document, data source of the sheet SUMMARY AND CURVES.
WORKING INSTRUCTIONS:
Project start
- Complete the required data in the upper rows of the SUMMARY AND CURVES sheet. (PROJECT, COMPANY, CONTRACT START, CUTOFF DATE,* Previous advance accumulated to the cut-off date)
- The DATABASE SHEET AND CURVES is configured according to the initial conditions of the project:
> List of documents to be taken as a measurement base (Coding, Description, Classification, Specialty, etc., in columns D to J). Do not let the column F (Main Code) empty.
  Classification Of Documents (Column J):
  Class Z: Class Z documents are those documents which COMPANY wishes to keep under close surveillance and, as such, COMPANY will review, comment and approve on all issues of Class Z documents.
  Class X: Class X documents are those documents that COMPANY wishes to receive for review and COMPANY may review and comment on the same. CONTRACTOR shall incorporate COMPANY's comments where
  Class O: Documents not identified as Class Z or X shall be produced and issued to COMPANY for information. COMPANY may review these documents as it deems necessary, and comments may be forthcoming on these documents. CONTRACTOR shall incorporate COMPANY's comments where received but shall otherwise proceed with development of documents.
> The budgeted man hours (MH), from which incidences are obtained by item (column K);
> Advance steps for measurement, defined in Annex X (columns Q to X); CAUTION: DO NOT LEAVE EMPTY CELLS (WITHOUT DATES) PUT A SCRIPT IN PLACE (-)
> Cut-off dates for measurement (columns Z to BT, ROW 3);
-The table and curves of the SUMMARY AND CURVES sheet are adjusted according to the criteria of grouping and consolidating documents.
- According to the Baseline schedule, in the DATA BASE AND CURVES sheet, the date of each advance step is programmed in the column corresponding to Baseline.This gives the base forward curve, which is fixed until the next Change of Commitment;
- Columns A-B-C are fields of use for YPF: do not delete or use;
Periodic update
> The cutting date is updated on the SUMMARY AND CURVES sheet. It is convenient that this date coincides with any of the weekly cutting dates of the DATA BASE AND CURVES sheet. All other updates are worked on the DATABASE AND CURVES sheet:
> The current revision of each document is updated in column M;
> Real/Trend dates are updated for each step of each document;(Columns R, T, V, X);
> IMPORTANT - CUTTING RULE: In fields Real / Trend, any completed (Real) step must be recorded at or equal to the cut-off date and any rescheduled step (Trend) must be recorded at a date after the cut-off date.
> In those steps not rescheduled (expected compliance at baseline date), the CON-012 will calculate the Trend according to baseline date;
> With the above information loaded, the CON-012 automatically gets the Real advance curve / Trend, the expected progress by item and by group, the table of the PROGRESS SUMMARY sheet, the current status of each document.
> Check the consistency of the information between the SUMMARY AND CURVES table, the O-P columns of the BASE DATA SHEET AND CURVES, and weekly cutting columns of the same sheet.
PROPÓSITO DE CADA PESTAÑA:
SUMMARY AND CURVES (Resumen y Curvas): Muestra el estado general del proyecto. Se utiliza como soporte para la certificación.
DATABASE AND CURVES (Base de Datos y Curvas): Hoja de seguimiento del progreso de cada documento; fuente de datos de la hoja SUMMARY AND CURVES.
INSTRUCCIONES DE TRABAJO
Inicio del proyecto
Completar los datos requeridos en las filas superiores de la hoja SUMMARY AND CURVES (PROYECTO, EMPRESA, INICIO DEL CONTRATO, FECHA DE CORTE, Avance previo acumulado a la fecha de corte).
La hoja DATABASE AND CURVES se configura según las condiciones iniciales del proyecto:
Lista de documentos que se tomarán como base de medición (Codificación, Descripción, Clasificación, Especialidad, etc., en las columnas D a J). No dejar vacía la columna F (Main Code).
Clasificación de documentos (Columna J):
Clase Z: Documentos que la COMPAÑÍA desea mantener bajo estrecha supervisión; por lo tanto, revisará, comentará y aprobará todas las emisiones de documentos Clase Z.
Clase X: Documentos que la COMPAÑÍA desea recibir para revisión; podrá revisar y comentar. El CONTRATISTA deberá incorporar los comentarios de la COMPAÑÍA cuando corresponda.
Clase O: Documentos no identificados como Clase Z o X serán emitidos a la COMPAÑÍA solo para información. La COMPAÑÍA podrá revisarlos y emitir comentarios si lo considera necesario; el CONTRATISTA deberá incorporarlos cuando se reciban, pero podrá continuar con el desarrollo de los documentos.
Las horas hombre presupuestadas (MH), a partir de las cuales se obtienen las incidencias por ítem (columna K); Los pasos de avance para medición definidos en el Anexo X (columnas Q a X); PRECAUCIÓN: NO DEJAR CELDAS VACÍAS (SIN FECHAS), PONER UN GUION “–” SI CORRESPONDE. Fechas de corte para la medición (columnas Z a BT, fila 3).
La tabla y las curvas de la hoja SUMMARY AND CURVES se ajustan según los criterios de agrupación y consolidación de documentos.
De acuerdo con el cronograma base (Baseline schedule), en la hoja DATABASE AND CURVES se programa la fecha de cada paso de avance en la columna correspondiente al Baseline. Esto genera la curva base proyectada (forward curve), que se mantiene fija hasta el siguiente cambio de compromiso (Change of Commitment).
Las columnas A-B-C son de uso exclusivo de YPF: no borrar ni usar.
Actualización periódica
Se actualiza la fecha de corte en la hoja SUMMARY AND CURVES. Es conveniente que esta fecha coincida con alguna de las fechas semanales de corte de la hoja DATABASE AND CURVES. Todas las demás actualizaciones se realizan en la hoja DATABASE AND CURVES:
Se actualiza la revisión actual de cada documento en la columna M.
Se actualizan las fechas Real/Trend para cada paso de cada documento (columnas R, T, V, X).
IMPORTANTE – REGLA DE CORTE: En los campos Real / Trend, cualquier paso completado (Real) debe registrarse en o antes de la fecha de corte, y cualquier paso reprogramado (Trend) debe registrarse con una fecha posterior a la fecha de corte.
En los pasos no reprogramados (cumplimiento esperado en la fecha Baseline), el CON-012 calculará automáticamente el Trend según la fecha Baseline.
Con esta información cargada, el CON-012 genera automáticamente la curva de avance Real / Trend, el progreso esperado por ítem y grupo, la tabla de la hoja PROGRESS SUMMARY y el estado actual de cada documento.
Verificar la consistencia de la información entre la tabla SUMMARY AND CURVES, las columnas O-P de la hoja DATABASE AND CURVES y las columnas de corte semanal de la misma hoja.