## Slide 1: IT0061 - ARGENTINA LNG – Export Pipelines System DOCUMENT FLOW MANAGEMENT BNT/PUMPCO

## Slide 2: DOCUMENTS WORKFLOW WITH CLIENT
ISSUE FOR
INFORMATION
ISSUE FOR
REVIEW
CLIENT
REVIEW
FINAL ISSUE
NOT APPROVED
APPROVED
100%
100%
60%
30%
FINAL APPROVAL by CLIENT
80%
APPROVED
WITH COMMENTS
Classification of Documents
Class X Documents
  Class X documents are those documents which CLIENT will review, comment and qualify on all issues of Class X documents. From the date of reception, the CLIENT has 5 working days to return the documentation to the BNT/PUMPCO, .
  BNT/PUMPCO shall incorporate CLIENT's comments but shall otherwise proceed with development of documents if no review, comment, APPROVAL or REJECTION was received, after notifying the CLIENT.
Class O Documents
  Documents not identified as Class Z or X shall be produced and issued to the CLIENT for information. CLIENT may review these documents as it deems necessary, and comments may be forthcoming on these documents.
  BNT/PUMPCO shall incorporate CLIENT's comments were received but shall otherwise proceed with development of documents.
Class X
Class O

## Slide 3: DOCUMENTS WORKFLOW MANAGEMENT
TRANSMITTALS from BONATTI/PUMPCO to CLIENT
The Documents will be uploaded in KBS (BNT Document Management System) by the Documents Owner.
KBS automatically sends the notification to BNT DC, who will send the official Transmittal by email to CLIENT.
The email will be generated by KBS, and all involved persons (BNT, PUMPCO, and CLIENT) will be in copy on the transmission according to the agreed Distribution Matrix.
The PUMPCO Responsible to manage Documents, clicks on the link inside the email and downloads the documents from KBS;
PUMPCO is responsible to storage them in PUMPCO System.
Documents, Transmittals and Reports can be downloaded from KBS at any time and for all the duration of the Project.
The Reports with Documents and Progress Status are automatically produced by KBS and they are timely updated.
BNT DC is responsible to upload documents in the Client System SDx2

## Slide 4: DOCUMENTS WORKFLOW MANAGEMENT
TRANSMITTALS to BONATTI/PUMPCO from CLIENT
CLIENT will send Commented/Approved Documents by email to BNT DC, in copy all involved persons according to the agreed Distribution Matrix.
The BNT DC registers the transmittal and uploads the documents in KBS.
KBS automatically sends the “Transmittal IN” notification to all involved persons (BNT and PUMPCO) according to the agreement.
The PUMPCO Responsible to manage Documents, clicks on the link inside the email and downloads the documents from KBS;
PUMPCO is responsible to storage them in PUMPCO System.
Documents, Transmittals and Reports can be downloaded from KBS at any time and for all the duration of the Project.
The Reports with Document and Progress Status are automatically produced by KBS and they are timely updated.

## Slide 5
Client System : SDx2 |  | BONATTI System : KBS |  | PUMPCO System : SharePoint | 
BNT DC | Cinzia Bini | BNT DC | Cinzia Bini | BNT DC | Cinzia Bini
 |  | BNT Project Team | All involved Bonatti personnels | BNT PEM | Giacomo Marinelli Massimo Ravaglia
 |  | PUMPCO Responsible | Julian Lell | PUMPCO Team | All involved PUMPCO personnels
SYSTEMS USED and APPOINTED PERSONNELS